## Phase 1 Fin Rescue
DITSOBOTLA LOCAL MUNICIPALITY
PHASE 1: FINANCIAL RESCUE
NO | FOCUS AREA | KEY ASSESSMENT FINDING (BASELINE) | KEY ACTIVITIES | RESOURCES REQUIRED | RESOURCES MOBILISED | RESPONSIBLE | START DATE | END DATE | KEY PERFORMANCE INDICATOR | PoE | BUDGET PARAMETER/ REVENUE TARGET/ SPENDING LIMIT | MUNICIPAL PROGRESS REPORT
[12 empty] | STEPS TAKEN | PROGRESS MADE | FINANCIAL IMPACT | OTHER NOTEWORTHY DEVELOPMENTS
PILLAR ONE: FINANCIAL MANAGEMENT
1 | BUDGET MANAGEMENT | The municipality approved unfunded budgets for 5 consecutive years. The municipality’s 2025/26 MTREF Budget is unfunded with R2,1bn, after all the municipality’s liabilities are considered. Budget-related policies reviewed annually but not assessed for financial viability (increased revenue and reduced expenditure). There is a risk that the December 2025 equitable share grant funding of the municipality might be withheld (MIF funds used to pay salaries Manipulation of the budget estimates, revenue over estimated and expenditure under estimated to budget for operating surpluses, but realise deficits (Budget not credible and realistic). | Prepare a credible 2025/26 Adjustment Budget aligned with the set FRP financial targets. | In house | In house | NCR, CFO | 2026-01-01 | 2026-02-28 | 2025/26 Adjustment Budget aligned with FRP Target | Approved 2025/26 Adjustment Budget | Repair and Maintenance: 2 per cent of OPEX Compliance to NT Budget Circular Alignment with Defined Budget Parameters nd FRP targets (See FRP Report for detail) Collection Rate 60%
|  |  | Review all budget related policies and assess for financial viability (increased revenue and reduced expenditure). | In house | PT Support | CFO | 2026-01-01 | 2026-03-01 | 100% of Budget Related Policies reviewed | Approved Budget Related Policies Council Resolution
|  |  | Prepare a 2025/26 Budget Funding Plan aligned with the FRP strategies. | In house | PT Support | CFO | 2026-01-01 | 2026-02-01 | 2025/26 BFP 100% FRP aligned | Approved 2025/26 BFP BFP Progress Reports
|  |  | Prepare a credible 2026/27 MTREF Budget aligned with the set FRP financial targets and in compliance with the NT Budget Circular. | In house | PT Oversight | CFO | 2026-01-01 | 2026-05-31 | 2026/27 MTREF Budget 100% aligned with FRP targets | Approved 2025/26 Budget Council Reslution
2 | BUDGET AND TREASURY OFFICE (BTO) | The BTO is lacking appropriate skills: Lacking appropriate skills, for example to prepare AFS. SCM = 4 positions filled. Revenue Management = 17 positions filled + 1 contract worker. Budget Management = 3 positions filled + 1 contract worker. Expenditure = 3 positions filled. Asset Management – no employees. | Provide training and advisory support in the areas of Budget and Revenue Management and Asset Management support. | MFIP Advisors | MFIP Advisors | CFO | 2026-01-01 | 2026-06-30 | Impoved BTO skills | Training schedule | Increased revenue and reduced expeniture to be realised through improved financial management efficiencies and systems with checks and balances in place
3 | REVENUE MANAGEMENT (METERED SERVICES AND VENDING) | No Revenue Enhancement Strategy in place. The Equitable Share for Free Basic Services is allocated to the NMMDM (average R13m per month) and not shared with DLM. Municipality does not possess employees with the skills set necessary to perform the function. The meter reading function has been outsourced for an extended period, therefore the require skills have not been maintained in-house. No reconciliations performed for prepaid vendors. Water Meters • Total of 18 101 meters in the systems of which only 448 (2,5 per cent) are read and billed with a total of 17 653 not read and billed. • Lack of water meters for replacements and new connections. • Vandalism of older existing meters for brass content. • Illegal connections and/or unmetered losses. Electricity Meters • Electricity meters are 1261 in total, 273 read and billed with a total of 988 unaccounted for. • Lack of meters for replacement and new connections. • Abridgement of electricity meters (legal and illegal). • Only around 10% of residential properties have meters. No meter audits performed for either Water or Electricity meters over at least the past 10 years. Challenge of prepaid meters which are not purchasing The municipality applied for the National Treasury smart meter grant and it was not granted due to failure to achieve the debt relief conditions, but the grant was actually going to assist the municipality to achieve as it was going to assist with revenue enhancement. Lack of control over the electricity services: Electricity revenue related services are performed by a service provider, Cigicel including monthly billing, and ultimately the recovery of electricity charges. The Service provider handles all electricity-related issues, and the municipality has limited control and oversight over the process. Broken/Faulty meters. Limitations of the Financial System: The municipality has moved to a new service provider and are encountering significant limitations with regards to the billing of consumers, over and above the limited meter information (No billing in 2022/23). | Conduct a complete meter audit. | In house | In house | CFO/ Technical Director | 2026-02-01 | 2026-05-31 | 100% of all connections and meters audted | Meter Audit Report | 2024/25 Actual + Growth (0,5 per cent) + NERSA Forecast (12.74 per cent) 800% increase in billed water meters (18,101 vs 444 currently billed) CPIX: 3,5 per cent 2% additional increase from: • Improved metering/ Reduced losses • Improved data integrity and billing • Improvement in controls leading to decreased illegal connections.
|  |  | Bill all 18101 existing water meters, based on accurate readings and realistic estimates. | In house | In house | CFO | 2026-01-01 | Monthly | 100% of all installed water meters billed | Water Billing Report
|  |  | Perform monthly reconciliations for all prepaid vendors. | In house | In house | CFO | 2026-01-01 | Monthly | 100% of vendor reconciliations completed | Monthly Vendor Reconciliations
|  |  | Prepare and submit an application for the National Treasury smart meter grant. | NT | N/A | NCR, CFO | 2026-01-01 | 2026-02-28 | Meter Grant Application Submitted | Meter Grant Application
|  |  | Address system issues with the billing of consumers, over and above the limited meter information. | In house | In house | NCR, CFO | 2026-01-01 | 2026-04-01 | 100% system issues solved | ICT Steercom Report on billing
|  |  | Introduce strict credit control (including for staff and councillors with long outstanding municipal debt). | In house | In house | NCR, CFO | 2026-01-01 | 2026-03-01 | 100% implementation of Crefdit Control Policy | Cut-Off lists
4 | REVENUE MANAGEMENT (PROPERTY RATES) | Valuation roll and the billing system contains errors: No VR reconciliation No property rates policy or by-law in place | Prepare the VR reconciliation and correct all variances | In house | NT VR Recon Tool | CFO | 2026-01-01 | Monthly | VR Reconciliation with 100% variances addressed | VR Reconciliation R98,4 million | Valuation Roll reconciled with Billing System + 2 per cent Calculated tariff for CPIX (3,5 per cent) adjustment Growth = 0,5 per cent (adjusted with poverty and unemployment Index) Collection Rate: 90 per cent (Jan-June 2026)
5 | REVENUE MANAGEMENT (COLLECTION) | Low revenue collection rates (44 per cent in 2024/25). Poor data integrity on the billing system. Lack of integration of the revenue value chain with town planning. Following a Court Order on 25 Oct’17, 8 big electricity pay directly to Eskom. Billing and financial system errors. | Integrate the Revenue Management Value Chain with Town Planning, Finance and Technical functions. | In house | In house | CFO | 2026-01-01 | 2026-05-31 | 100% integration of Meter Management Value Chain | Meter Management Integration Progress Reports | Collection Rate 60%
|  |  | Implement targeted credit control. | In house | In house | CFO | 2026-01-01 | Daily/ Monthly | Improved Collection Rate | Collection reports | Collection Rate 60%
6 | DEBTORS MANAGEMENT | Net debtors’ days increased from 992 days in 2019/20 to 1060 days in 2024/25. Debtors book could be overstated, and not reviewed regularly to determine how much can realistically be collected. Municipality has weak controls in debtor’s management. Some of the major debtors are councillors, staff and government institutions which do not pay their utilities on time. No credit control policies in place to guide provision of services to non-paying customers. Resistance to implement credit control measures. Net debtors’ days increased from 992 days in 2019/20 to 1060 days in 2024/25. | Electricity of consumers, government institutions, staff and councillors to be cut, after letter has been send to make payment by certain due date. | In house | In house | NCR, CFO | 2026-01-01 | Monthly | Improved Collection Rate | Final Reminder letters and cut-off lists | Debt Impairment: 100 per cent of billed revenue minus realistic Collection Rate
|  |  | Implement a comprehensive case management system to track and prioritise customer issues, requests, and complaints. | In house | In house | CFO | 2026-01-01 | 2026-06-30 | Functional Case Management System | IA Report NCR confirmation
7 | COST-REFLECTIVE TARIFFS | All trading services function with operating deficits. Non-cost reflective tariffs. The municipality does not have an approved tariffs policy or structure in place. | Verify tariff increases for cost-reflectiveness. | In house | NT Tariff Assessment Tool | NCR, CFO | 2026-01-01 | 2026-05-31 | All tariffs verified | Tariff Assessment Report | Increased revenue and reduced expeniture to be realised through improved financial management efficiencies and systems with checks and balances in place
|  |  | Develop and approve tariff setting model. | In house | In house | CFO | 2026-01-01 | 2026-05-31 | Tariff Setting Model Approved | Approved Tariff Setting Model | Increased revenue and reduced expeniture to be realised through improved financial management efficiencies and systems with checks and balances in place
|  |  | Revised tariffs to be approved with budget. | In house | PT | CFO | 2026-01-01 | 2026-05-31 | Cost reflective tariffs approved | Approved 2026/27 MTREF Budget | Increased revenue and reduced expeniture to be realised through improved financial management efficiencies and systems with checks and balances in place
|  |  | Update and approval of Tariff Policy and Tariff Structure to make provision for the application of cost-reflective tariffs in a phased approach. | In house | PT | CFO | 2026-01-01 | 2026-05-31 | Approved Tariff Policy and Structure | Approved Tariff Policy and Structure | Increased revenue and reduced expeniture to be realised through improved financial management efficiencies and systems with checks and balances in place
8 | SUPPLY CHAIN MANAGEMENT | The SCM unit is fairly functional and currently consists of 4 officials, however, there is a concern with regards to the competence levels of the staff members. SCM Committees not properly functional. No procurement plan could be submitted. Outdated SCM related policies. Oversight of the SCM function by accounting officer and Council is not consistent due to instabilities in these posts. SCM procedures are not documented. | SCM Policy to be updated and approved by council with the Budget Process (in line with the latest SCM regulations). | In house | PT | NCR, CFO | 2026-01-01 | 2026-02-28 | 100% compliant SCM Policy | Approved SCM Policy | Increased revenue and reduced expeniture to be realised through improved financial management efficiencies and systems with checks and balances in place
|  |  | Compile procurement plans in line with NT MFMA Circular No. 62 | In house | PT | CFO | 2026-01-01 | 2026-02-26 | 100% compliant Procurement Plan | Approved Procurement Plan Council resolution | Increased revenue and reduced expeniture to be realised through improved financial management efficiencies and systems with checks and balances in place
|  |  | Take all reasonable steps to ensure that proper mechanisms and separation of duties are in place within the supply chain management system to minimise the likelihood of fraud, corruption, favouritism and unfair and irregular practices. | In house | PT MFIP Advisor | CFO | 2026-01-01 | 2026-03-31 | Value-for-Money procurement | Approved SCM Internal Controls | Increased revenue and reduced expeniture to be realised through improved financial management efficiencies and systems with checks and balances in place
9 | COST CONTAINMENT AND CASH FLOW MANAGEMENT | No compliant Cost Containment Policy. Cash flow management committee not in place. Weak controls over cash and bank. No financial discipline. Irregular appointment of security service provider and inflated and unnecessary cost. | Cost containment policy to be revised aligned with the 2019 NT Regulations on Cost Containment. | In house | PT | NCR, CFO | 2026-01-01 | 2026-02-28 | Fully compliant Cost Containment Policy | Approved Cost Containment Policy Council resolution | Targeted ratios: • Cash Coverage: 0 Months • Current Ratio: 0.7:1 Maintain savings from 2025/26 BFP and ensure full compliance with regulations + further savings
|  |  | Implement the Cost Containment Policy and report progress against set saving targets/ Phased-in implementation of cost cutting measures on allowances and entertainment expenses. | In house | In house | NCR, CFO, Senior Managers | 2026-01-01 | Monthly | Cost contained in line with FRP expenditure targets | Cost Containment Progress Reports | Increased revenue and reduced expeniture to be realised through improved financial management efficiencies and systems with checks and balances in place
|  |  | Establish a cash flow management committee to ensure cost-containment measure are implemented and monitored effectively. | In house | In house | NCR | 2026-01-01 | 2026-01-31 | Functional Cash Flow Management Committee | Cash Flow Committee ToR | Increased revenue and reduced expeniture to be realised through improved financial management efficiencies and systems with checks and balances in place
|  |  | NCR to authorize all bank transactions within framework of strict internal controls and legislative compliance. | In house | NCR | NCR | 2026-01-01 | Daily | 100% of bank transactions authorised by NCR No unauthorised expenditure | Expenditure records | Increased revenue and reduced expeniture to be realised through improved financial management efficiencies and systems with checks and balances in place
10 | FINANCIAL CONTROL ENVIRONMENT | Consultants are contracted for critical finance functions without proper performance monitoring. Financial system challenges have affected billing and reporting since 2020. Staffing constraints in critical finance roles. Poor internal financial controls. | Engage with the service provider to analyse and identify the root cause for billing complications (consider the different systems follows difference processes, i.e. similar issues identified at other municipalities using the same system/s. | In house | In house | NCR, CFO | 2026-01-01 | 2026-03-31 | 100% billing system issues resolved | Meeting minutes | Increased revenue and reduced expeniture to be realised through improved financial management efficiencies and systems with checks and balances in place
|  |  | Develop and implement internal financial controls (segregation of duties, etc.) | In house | In house | NCR, CFO | 2026-01-01 | 2026-02-28 |  | Approved internal financial controls | Increased revenue and reduced expeniture to be realised through improved financial management efficiencies and systems with checks and balances in place
11 | mSCOA | Non-adherence to MSCOA legislation. Key Functional mSCOA Modules not implemented. Lacking funding to develop the IT environment. No functional Steering committee for MSCOA implementation. No mSCOA Champion. No mSCOA Road Map developed. Data Strings not credible. | Establish mSCOA Steering Committee. | In house | In house | CFO | 2026-01-01 | 2026-01-31 | mSCOA Sterrcom ToR | mSCOA Sterrcom ToR | Increased revenue and reduced expeniture to be realised through improved financial management efficiencies and systems with checks and balances in place
|  |  | Development of mSCOA Road Map. | In house | In house | CFO | 2026-01-01 | 2026-02-28 | mSCOA Roadmap approved and implemented | mSCOA Roadmap | Increased revenue and reduced expeniture to be realised through improved financial management efficiencies and systems with checks and balances in place
|  |  | Develop a mSCOA compliant chart of accounts (trial balance) - Also refer to budget section | In house | In house | CFO | 2026-01-01 | 2026-03-31 | Approved mSCOA Chart of Accounts | Approved mSCOA Chart of Accounts | Increased revenue and reduced expeniture to be realised through improved financial management efficiencies and systems with checks and balances in place
|  |  | Facilitate periodic in-house and external training on the use and implementation of the mSCOA charts. | In house | In house SAGE | CFO | 2026-01-01 | Monthly | Improved mSCOA compliance | mSCOA Traing Schedule | Increased revenue and reduced expeniture to be realised through improved financial management efficiencies and systems with checks and balances in place
12 | FINANCIAL REPORTING | Lack of capacity and competence to carry out the financial reporting function. Inaccurate financial reporting The financial reporting function has been grossly mishandled by consultants as evidenced by the consecutive disclaimer of opinions from AGSA. The underlying financial records for financial reporting affected by IT systems challenges. Non-adherence to AGSA and NT submission timeframes. | Monitor in-year reporting and MFMA compliance. | In house | PT Oversight | NCR, CFO | 2026-01-01 | Ongoing | 100% reporting compliance | PT Oversight Report | Increased revenue and reduced expeniture to be realised through improved financial management efficiencies and systems with checks and balances in place
|  |  | Strengthen internal control measures to ensure that proper record keeping of all financial information is always kept to avoid the late submission of AFS which results in non-compliance. | In house | In house | CFO | 2026-01-01 | 2026-02-28 | 100% record of source documentation | AG Reports
13 | EXPENDITURE MANAGEMENT | Creditors days increased from 2087 days in 2022/23 to 3188 days in 2024/25 which means the Municipality is taking a very long time to settle amounts owed. No grant management policy in place. Approved for Eskom Debt Relief, but not complying (Risk that Eskom may take over). Non-payment of services within 30 days of receipt of the invoice as required by the MFMA. Poor relationship between municipality and suppliers/ creditors due to non-payment. Irregular payments made from the bank accounts | Payment arrangement to be signed with all major creditors including Eskom. | In house | In house | NCR, CFO | 2026-01-01 | 2026-02-28 | 100% payment agreements with top 5 creditors | Signed payment agreements Contracted Services maximum: R24,2 million | 10% reduction in water/ electricity losses through improved metering and decreasing illegal connections Contracted Services – Norm 2-5 per cent of OPEX: <6,5 per cent Other expenditure: CPI increase (3 per cent) + Growth (0,5 per cent) +5 per cent reduction from cost containment measures
|  |  | Ensure creditors paid only for legitimate services rendered to the municipality. | In house | In house | NCR | 2026-01-01 | Daily | 100% legitimate payments | IA Report AG Reports | Increased revenue and reduced expeniture to be realised through improved financial management efficiencies and systems with checks and balances in place
|  |  | Avail expert to verify the monthly Eskom account. | In house | PT | NCR | 2026-01-01 | Monthly | 100% Eskom accounts verified | Copies of certified invoices
|  |  | Strengthen the finance department's oversight to ensure compliance with the Municipal Debt Relief conditions. | In house | In house | NCR, CFO | 2026-01-01 | 2026-02-28 | Improved Eskom Debt Relief Compliance | Eskom Debt Relief Compliance Plan
|  |  | Consequence Management for misappropriation of funds. | In house | In house | NCR | 2026-01-01 | Ongoing | No misappropriation of funds | NCR Report
14 | ASSET MANAGEMENT | No standalone asset management unit that ensures assets are maintained and safeguarded. Sound asset management practices like physical verifications not implemented as there is no standalone asset management unit. Asset management relating to capital projects does not align with the critical needs of the municipality. No up-to-date Asset Management Policy FAR not annually updated. | Appointment of asset custodians and provide training on asset insurance, audits, reporting, and FAR. | In house | In house MFIP Advisor | CFO | 2026-01-01 | 2026-04-30 | Asset management custodians appointed/ seconded | AM appointment letters | Increased revenue and reduced expeniture to be realised through improved financial management efficiencies and systems with checks and balances in place
|  |  | Asset management policy to be compiled and approved with the budget process. | In house | In house | CFO, Technical Director | 2026-01-01 | 2026-05-31 | Approved AM Policy | Approved AM Policy
15 | INDIGENT MANAGEMENT | Poor indigent household registration. Outdated Indigent Policy. No verification of indigent debtors. No appropriate write-offs of Indigents Debt. FBS allocations could not be confirmed. | Review the indigent policy to confirm it is aligned with the operations of the municipality and approved with the budget. | In house | In house | CFO | 2026-01-01 | 2026-04-30 | Approved Indigent Management Policy Council resolution | Approved Indigent Management Policy Council resolution | Increased revenue and reduced expeniture to be realised through improved financial management efficiencies and systems with checks and balances in place
|  |  | Only make Free Basic Services (FBS) available to registered indigent households. | In house | In house | CFO | 2026-01-01 | 2026-03-31 | All FBS limited to Indigent Households | Approved FBS Policy
|  |  | Assess Indigents Debt, and submit write-off schedule to Council for approval. | In house | In house | CFO | 2026-01-01 | 2026-06-30 | 100% irrecoverable indigent debt written off | Indigent Debt Write-Off Report
PILLAR TWO: SERVICE DELIVERY AND INFRASTRUCTURE DEVELOPMENT
1 | MASTER PLANNING | Senior Management positions in the service delivery unit are vacant and this hampers effective service delivery. | Appoint qualified technical personnel in particular the Director Technical Services | In-house | In-House | MM, NCR | 2026-01-01 | 2026-12-30 | Appointment of the Technical Director | Letter of Appointment of Technical Director | Financial benefits accruing from improved service delivery efficiencies
|  | The municipality does not have updated Master Plans and Maintenance Plans in place. | (1) Development and Implementation of Property Plant and Equipment Maintenance Plan; (2) Audit of current infrastructure to determine state, taking into consideration service backlogs and long-term strategy aligned to the operating model IDP, budget and long-term financial plan to support asset register(3) Appoint qualified expert consultants for the development of Master Plans covering Water, Sanitation, Electricity, Roads, Stormwater, Waste Management, and Human Settlements | MISA | MISA | MM, NCR Service Delivery Expert | 2026-01-01 | 2026-12-30 | (1) NRS 047 (Electricity) NRS 048 (Electricity) Water (Burst Frequency) (2) Conditional Assessment Rating for each asset Remaining useful life of each assets (3) Master Plans Electricity, Roads and Stormwater | (1) Maintenance Plan (2) GRAP Compliant Asset Register(3) Master Plans Electricity, Roads and Stormwater | Financial benefits accruing from improved service delivery efficiencies
|  | The National Spatial Development Framework requires that municipal SDF is reviewed at least every five years to remain aligned with national and provincial policies. SDF provides the policy framework that underpins the municipal Land Use Scheme (LUS) and its absence means the municipality is not able to plan accordingly and appropriately | Update the SDF | In-house | In-House | MM, NCR | 2026-01-01 | 2026-12-30 | Updated SDF | Updated SDF | Financial benefits accruing from improved service delivery efficiencies
2 | CAPITAL AND GRANT FUNDED PROJECTS | Procurement committees appointed to be responsible for grant approved projects are in place but not effective. (Inconsistency due to new committees being appointed with every change in MM) Persistent non- compliance with legislation 5% of MIG Grant not allocated for Waste Management 8% of MIG Grant not allocated for Operations and Maintenance Municipality not spending 100% of allocated grants (R62m unspent grants 2025) Municipality not applying for all grants (Municipality only recorded allocation of MIG and INEP only) Municipality not spending 100% on all allocated grants | Train employees in the Project Planning Unit to (1) develop project specifications to service in the Bid Specification Committee. (2) Train employees in the service delivery unit to conduct evaluation of submissions to be submitted to the Bid Evaluation Committee. | In-house | In-House | MM, NCR | 2026-01-01 | 2026-12-30 | (1) Monthly Register of Specification serving in the Bid Specification Committee. (2) Confirmation that 100% of Bid Committee Members are trained. (3) Confirmation that 100% of PMU Members are trained | Training Schedule, Register of Trained Personnel | Financial benefits accruing from improved service delivery efficiencies
|  |  | Conduct quarterly performance review for the project management unit and grant management. Intensify monitoring of compliance to legislation by management | In-house | In-House | MM, NCR | 2026-01-01 | 2026-12-30 | Actual Grant Percentage Expenditure vs Projected Expenditure | Grant Performance Report | Actual Grant Percentage Expenditure vs Projected Expenditure
|  |  | Municipality must prepare business plan for utilizing (1) 5% of MiG for Waste Management; (2) 8% of MIG for Operations and Maintenance; (3) Infrastructure Skills Development Grant; (4) Smart Metering Grant; (5) Energy Efficiency Grant; (6) Water Services Infrastructure Grant; (7) Neighbourhood Development Grant; (8) Budget Facility for Infrastructure. | In-house | In-House | MM, NCR | 2026-01-01 | 2026-12-30 | Submission of application for grant funding | Funding Business Plan, application and proof of submission to the Sector Department | Financial benefits accruing from improved service delivery efficiencies
|  |  | Spend 100% of all grants allocated. | In-house | In-House | MM, NCR | 2026-01-01 | 2026-12-30 | Actual Grant Percentage Expenditure vs Projected Expenditure | Grant Performance Report | Actual Grant Percentage Expenditure vs Projected Expenditure
|  | Payments Process for contractors is delayed due to validation process by CoGTA/MISA on how the service providers were appointed and confirmation of work done. The delay caused by this process result in the service leaving site | MISA and COGTA to propose a process plan which should be incorporated in the implementation plan for the contractor appointment and timeslines performance parameters during project execution. | In-house | In-House | MM, NCR | 2026-01-01 | 2026-12-30 | Register of incomplete projects with project finance and technical performance | Register of incomplete projects with project finance and technical performance | Outstanding payments for all completed work must be zero.
3 | BULK WATER SUPPLY AND RETICULATION | Inadequate water supply to meet demand due to low borehole yields (11,6Ml/day vs demand of 19Ml/day), water losses and electricity loadshedding affects Water Losses @ 58% | Financial model targets an increase in revenue from R10m to R92m. The reduction in losses by 28% through meter reading and presure management, meter and customer audits | In-house | In-House | MM, NCR | 2026-01-01 | 2026-12-30 | Water Pressure during different times of the day Number of meters, types of meters, readable meters, visible meters, broken meters, leaking meters | Water Loss Calculation Meter Audit Report (number of meters vs customers, Billing meters, Estimates, Broken Meters, Number of meters that need to be replaced) | Financial benefits accruing from improved service delivery efficiencies
|  | The municipality is unable to account for water it purchases; Losses are not recorded; therefore, it is difficult to quantify them and identify cost-saving solutions | Conduct monthly water balance reports comparing bulk supply, metered consumption, and losses to quantify distribution losses and identify areas for intervention; (2) Conduct a technical assessment to identify and document all strategic sites for the installation of bulk water and zone meter and Rank sites based on water loss potential, population served, and network criticality. | In-house | MISA | MM, NCR | 2026-01-01 | 2026-12-30 | No. of bulk supply points vs No of bulk meters read | Reconciliation of water purchased with water dispatched; Water Loss Calculation | Financial benefits accruing from improved service delivery efficiencies
|  | The municipality is not quantifying water losses. | The operations and maintenance staff should urgently be trained in schemes operations, opening and closure of valves | In-house | MISA | MM, NCR | 2026-01-01 | 2026-12-30 | Maintenance Curriculum Employees Training based on the Mainteance Curriculum Developed | Trained Officials Register Qualifications and Certicates of Participation | Financial benefits accruing from improved service delivery efficiencies
|  | Leakage of old asbestos pipeline Community protests incorrectly directed to the local instead of the District on powers and functions outside the competency of municipality | Conduct a full audit to identify all asbestos pipeline sections in the network | In-house | MISA | MM, NCR | 2026-01-01 | 2026-12-30 | km of asbestos pipes and sizes needing replacement | Audit Report for on pipelines | Financial benefits accruing from improved service delivery efficiencies
|  |  | Rank sections based on leakage frequency, proximity to high-risk areas, and critical water supply zones. | In-house | MISA | MM, NCR | 2026-01-01 | 2026-12-30 | leakage frequency proximity to high risk areas criticality rating of the supply | Pipe Replacement Ranking Report | Financial benefits accruing from improved service delivery efficiencies
|  |  | Ensure all public complaints are efficiently received, tracked, and directed to the appropriate authority for resolution | In-house | MISA | MM, NCR | 2026-01-01 | 2026-12-30 | Customer Service Charter Response Times SDBIP Performance Measures | Customer Service Performance Report (e.g. SmartGov, GovSuite) | Financial benefits accruing from improved service delivery efficiencies
|  | District Municipality unable to effectively provide water services as per the Court judgement due financial constraints | Development of standard operating procedures for work packages that need to be undertaken. | In-house | MISA | MM, NCR | 2026-01-01 | 2026-12-30 | Service Level Agreement Signed | Service Level Agreement Signed | Financial benefits accruing from improved service delivery efficiencies
|  | Magalies Water billing both the municipality and the District for water provided through boreholes | Review and update the water supply and billing agreement between the Ditsobotla LM District, and Magalies Water to clearly define responsibilities and billing points. | In-house | MISA | MM, NCR | 2026-01-01 | 2026-12-30 | Service Level Agreement Signed | Service Level Agreement Signed | Financial benefits accruing from improved service delivery efficiencies
4 | BULK ELECTRICITY SUPPLY AND RETICULATION | The Municipality is licenced to supply electricity to the following areas: Lichtenburg, Blydeville, Burgersdrop and Coligny Electricity losses - 85% in 2024/25FY. Norm is 7-10% • Load is not managed • Remote geyser system is not operational • Challenges with metering and metering efficiencies | (1) Sign Distribution Agency Agreement; (2) Undertake a cost of supply study; (3) Geyser control - municipality can save approx. R32 million per year for 10,000 geysers. Install a system for hot water load management Participate in Eskom Performance Contracting for Load management | In-house | MISA | MM, NCR | 2026-01-01 | 2026-12-30 | (1) Signed Distribution Agency Agreement; (2) Cost of Supply Study and Tariffs; (3) No. of households with geysers vs Relay control for available systems | (1) Signed Distribution Agency Agreement; (2) Cost of Supply Study and Tariffs; (3) Hot Water Load Management Project Progress Report | Hot Water Load Management Project Progress Report
|  |  | Installation/repair of 9000 electricity meters which were not reading and billing before in order to achieve the FRP financial target | In-house | MISA | MM, NCR | 2026-01-01 | 2026-12-30 | Financial Model - R17.47m new additional revenue. 9000 meters with the assumption of minimum billing of R2000 | Meter installation/repair progress report. | Financial Model - R17.47m new additional revenue. 9000 meters with the assumption of minimum billing of R2000
5 | WASTE AND REFUSE REMOVAL | Three landfill sites (Itsoseng, Tlhabologang, and Biesiesvlei) are non-functional and have been issued waste management licenses for closure and rehabilitation. Coligny and Lichtenburg landfill have not been maintained properly and both are not compliant with regulations for landfill sites. | Prioritize billiing for waste disposed using the vehicle type or weight pads or weightbridges to generate additional revenue of R1m | In-house | In-House | MM, NCR | 2026-01-01 | 2026-12-30 | Waste Management By-Law Workshop, Consultations, Approval | Approved Waste Management By-Laws | Additional Waste Revenue of approximately R85 000 per month.
6 | PLANNING AND BUIDING CONTROL | Itekeng Extension 3) township has been establishment with objections (whereas Itekeng Extension 2 establishment with pending EIA | Expedite the completion and approval of the pending EIA for Itekeng Extension 2 to ensure legal compliance | In-house | In-House | MM, NCR | 2026-01-01 | 2026-12-30 | EIA Report and Approval | ROD and Approved EIA Report | Financial benefits accruing from improved service delivery efficiencies
7 | FLEET MANAGEMENT | No fleet management policy | Develop and implement an Integrated Monitoring and Reporting System (IMRS) to track performance, resource utilization, and expenditure across all service delivery departments. | In-house | In-House | MM, NCR | 2026-01-01 | 2026-12-30 | Fleet Management Policy | Fleet Management Policy | Financial benefits accruing from improved service delivery efficiencies
|  | Inadequate number of refuse vehicles to efficiently service the community Increasing costs make it a challenge to operate efficiently | (1) Implement cost-control measures and route optimization to improve collection efficiency; (2) Purchase refuse vehicle using MIG Waste Management portion. | In-house | In-House | MM, NCR | 2026-01-01 | 2026-12-30 | (1) Cost-control measures and route optimization; (2) Purchase of specialised waste management vehicle. | Cost-control measures and route optimization | Financial benefits accruing from improved service delivery efficiencies. Apportion MIG allocation for Waste Management vehicle.
8 | HOUSING DELIVERY | In 2016/2017 only 69 units were allocated in Springbokpan; 29 in Matile and 1 in Meetmakar. Houses were left at foundation levels by service providers for example in Itsoseng. | (1) The municipality must update its housing pipeline based on confirmed allocations to accelerate project implementation. (2) Engage the Department of Human Settlements to enforce contractual obligations and compel service providers to complete the stalled housing projects. | In-house | In-House | MM, NCR | 2026-01-01 | 2026-12-30 | Outstanding Projects List | Beneficiary Management Report | Financial benefits accruing from improved service delivery efficiencies
9 | ROADS AND STORMWATER | Severe deterioration of the roads with potholes and flooding of properties due to blocked or inadequate stormwater systems. Gravel roads were not constructed nor maintained | (1) Municipality to develop and implement a plan on pothole repairs, drainage upgrades, and regular clearing of stormwater channels to prevent flooding. (2) Implement a routine maintenance schedule to ensure accessibility and durability of all gravel routes. | In-house | In-House | MM, NCR | 2026-01-01 | 2026-12-30 | Parameters as defined in the SDBIP for Roads and Stormwater | Completed work vs Planned as per SDBIP | Financial benefits accruing from improved service delivery efficiencies
10 | SECURITY SERVICES | Vandalism of municipal property Riots and Protests | Conduct quarterly community engagement sessions and awareness campaigns in collaboration with ward committees | In-house | In-House | MM, NCR | 2026-01-01 | 2026-12-30 | No. of meetings held | Meetings Schedule, Agenda, Minutes | Financial benefits accruing from improved service delivery efficiencies
11 | LOCAL ECONOMIC DEVELOPMENT | There is a high level of unemployment skills shortage and inequalities. Huge backlog in the provision of social services, infrastructure, and economic activities. | Implement labor-intensive projects to prioritize local employment during infrastructure rollout | In-house | In-House | MM, NCR | 2026-01-01 | 2026-12-30 | Man hours for grant projects | Report on man hours on capital projects | Financial benefits accruing from improved service delivery efficiencies
|  | The municipality does not have funds to budget for LED projects and programmes. | Establish a relationship with mining houses and private sector to leverage on the possible implementation of LED through Social Labour Plan (SLP) and Corporate Social Investment (CSI) or Private Public Partnership (PPP) opportunities. | In-house | In-House | MM, NCR | 2026-01-01 | 2026-12-30 | No. of jobs to be created and infrastructure investment value | Social Labour Plan | Financial benefits accruing from improved service delivery efficiencies
|  | The unit functions on minimal operational budget. | Develop LED stakeholder matrix and establish local LED forum, to create a platform for discussion of possible LED solutions. | In-house | In-House | MM, NCR | 2026-01-01 | 2026-12-30 | Stakeholder Matrix No. of LED Forum Meetings | Meetings Schedule, Agenda, Minutes | Financial benefits accruing from improved service delivery efficiencies
|  |  | Participate in District Development Model (DDM) economic repositioning workstream, to contribute towards the formulation of district one plan catalytic projects. | In-house | In-House | MM, NCR | 2026-01-01 | 2026-12-30 | No. of DDM Meetings | Meetings Schedule, Agenda, Minutes | Financial benefits accruing from improved service delivery efficiencies
PILLAR THREE: GOVERNANCE
1 | Governance Model (Council and Sect. 79 & 80 Committees) | Municipal Council not sitting to date for the financial year 2025/26 except for the special meeting held for the election of the Speaker and Mayor; The municipality’s council and its committees are not yet functional; Rules and Orders outdated; Resolutions register or a system to track resolutions not updated; The code of conduct that addresses ethical behavior by councillors is not implemented; Councillors and staff in arrears for service provided and rates in the amount of R1.1 million and R13 million respectively; Lack of policies and systems in place to enforce Code of Conduct; No consequence management against councillors and staff in arrears; Non-compliance and failure to fulfil the Constitutional obligations; Economic decline and high unemployment rates; Committees of council do not quorate due to non-attendance of meetings by councillors; There is no record of councillors’ declaration of interest; There is Political Interference and free for all in recruitment process of staff and SCM functions Non-compliance with statutory prescripts Forensic investigations conducted into allegations of Maladministration, Fraud and Corruption Investigations reports cannot be located No evidence that the recommendations of the investigations were implemented Insecure and unsafe working environment. Council has not approved and implemented a stakeholder engagement strategy and public participation policy although the draft is in place awaiting Council approval Non approval and Failure to timeously prepare and process statutory reports i.e. Section 71, Section 52(b) and (b) MFMA Reports, AFS, Annual reports, SCM Regulation 6 Reports and Section 32 investigation Reports Section 71 MFMA Report not approved in line with calendar of Council Ward committees not functional and ward committee operational plans not provided | Maintain record of nonattendance of Council and committee meetings to enable enforcement of Code of Conduct for councillors; | In-house | In-house | NCR/Director: Corporate Services | 2026-01-01 | 28/02/2025 | Fully functional council and committees | Minutes of Council and committee meetings | Financial benefits to be realised through improved governance efficiencies and systems with checks and balances in place
|  |  | Quarterly reporting to Council on nonattendance of Council and committee meetings, and enforcement of Code of Conduct for councillors; | In-house | In-house | NCR/Director: Corporate Services | 2026-01-01 | Quarterly | Fully functional council and committees | Quarterly reports and Minutes of Council and committee meetings | Financial benefits to be realised through improved governance efficiencies and systems with checks and balances in place
|  |  | Recover 50% from monthly salary for each councillor in arrears through payroll deductions; | In-house | In-house | NCR/Director: Corporate Services | 2026-01-01 | Monthly | Reduction in arrears for councillors and payment of current accounts | Monthly Financial reports by CFO | Increase revenue
|  |  | Recover 25% from monthly salary for each staff member in arrears through payroll deductions and payment arrangements which must include honouring of current accounts; | In-house | In-house | NCR/Director: Corporate Services | 2026-01-01 | Monthly | Reduction of arrears and payment of current accounts by staff | Monthly Financial reports by CFO | Increase revenue
|  |  | Approval of the stakeholder engagement strategy by Council; | In-house | In-house | NCR/Director: Corporate Services | 2027-01-01 | 28/02/2027 | Improved accountability and good governance practices | Council approved reports and sugned resolutions | Financial benefits to be realised through improved governance efficiencies and systems with checks and balances in place
|  |  | Finalise the establishment of the municipal Town-Planning Tribunal; | In-house | In-house | NCR/Director: Community Services | 2026-01-01 | 28/02/2026 | Tribunal established and planning processes implemented | Approved establishment and signed resolution | Financial benefits to be realised through improved governance efficiencies and systems with checks and balances in place
|  |  | Establish the Disciplinary Board and the Audit committee; | In-house | In-house | NCR/Manager: Internal Audit | 2026-01-01 | 31/03/2026 | DB and Audit committees established and functional | Approved reports on establishment | Financial benefits to be realised through improved governance efficiencies and systems with checks and balances in place
|  |  | Secure the forensic investigation reports from the service provider and table same in the Council; | In-house | In-house | NCR/MM | 2026-01-01 | 31/03/2026 | Recovered forensic investigations reports | Approved Council report and signed resolution | Financial benefits to be realised through improved governance efficiencies and systems with checks and balances in place
|  |  | Request the Special Investigating Unit to investigate Maladministration, Fraud and Corruption including to conclude investigations initiated by the Public Protector including security contracts for the past five years; | In-house | SIU | NCR | 2026-01-01 | Monthly until end of investigations | Investigations continuing according to plan | SIU investigations report | Financial benefits to be realised through improved governance efficiencies and systems with checks and balances in place
|  |  | Review all reinstated/re-employment of officials through or inconsistent with Court Orders/Default judgements; | In-house | COGTA | NCR | 2026-01-01 | 30/06/2026 | Irregular decisions reversed | Reviewed reports | Financial benefits to be realised through improved governance efficiencies and systems with checks and balances in place
2 | SYSTEM OF DELEGATION | No approved system of delegations by the municipal Council leading to administrative and operational inefficiencies, no checks and balances, irregular and unlawful decisions and non-compliance with statutory prescripts No sub-delegation of authority to staff leading to Staff executing work without delegated authority No delegation register Selective acceptance of sourced external legal opinions based on personal interest | Develop process plan for review of the system of delegations | In-house | SALGA/COGTA | Director: Corporate Services | 2026-01-01 | 31/03/2026 | Process plan in place | Council approved process plan and signed resolution | Financial benefits to be realised through improved governance efficiencies and systems with checks and balances in place
|  |  | Define the specific roles and areas of responsibilities for each political structure, political office bearer and of the Municipal Manager | In-house | SALGA/COGTA | Director: Corporate Services | 2026-01-01 | 31/03/2026 | Roles and Responsibilities defined | Council approved report and signed resolution | Financial benefits to be realised through improved governance efficiencies and systems with checks and balances in place
3 | LITIGATION AND CONTINGENT LIABILITY | The municipality has a huge contingent liability potential exposure of about R63 770 076.34 million No litigation strategy in place No delegated authority to initiate and oppose litigation for or against the municipality Irregular and unlawful decisions by structures, executive and the administration due to inadequate legal advice/support. No updated litigation register Default judgements leading to Writs of Execution, Attachment of assets, Attachment of bank accounts and equitable shares Failure to honour settlement agreements with law firms for services rendered Lack of instructions on Court applications from Finance Directorate Legal fees paid by the Municipality to service providers in respect of legal services during the: • 2022/23 financial year were R 5 020 401.06 million. Budget 2022/23 FY: R3.2 million • 2023/24 financial year were R 1 310 345.26 million. Budget 2023/24: R3.2 million • 2024/25 financial year were R16 530 997.22 Budget 2024/25 FY; R3.6 million • 2025/26 financial year (First two months) R7 648 593.90 • Budget 2025/26 FY: R3.6 million Invoice processing systems with checks and balances and payment validation collapsed Law firms submitting invoices where there is no (or minimal) paper trail to confirm services rendered Outstanding invoices to the value of R5 213 316.40 No records of work done Fruitless and Wasteful intra-institutional litigation against councillors by other councillors and between Municipal manager against the political office bearers of the municipality Costs awarded in the personal capacity from councillors not collected | Delegation of powers and functions to initiate and oppose litigation for or against the municipality; | In-house | In-house | NCR/Director: Corporate Services | 2026-01-01 | 28/02/2026 | Delegated authority in place | Approved Council report and signed resolution | Financial benefits to be realised through improved governance efficiencies and systems with checks and balances in place
|  |  | Audit and investigate the state of Default/Court judgements, writ of execution, attachment of assets, attachment of equitable share and bank accounts; | In-house | In-house | NCR/Director: Corporate Services | 2026-01-01 | 31/03/2026 | Audit and investigation completed/Reverse all irregular and unlawful decisions | Audit report submitted to Municipal Manager | Financial benefits to be realised through improved governance efficiencies and systems with checks and balances in place
|  |  | Review and renegotiate settlement agreements with law firms for service rendered; | In-house | In-house | NCR/Director: Corporate Services | 2026-01-01 | 31/03/2026 | Court applications withdrawn | Signed re-negotiated settlement agreements and monthly proof of payments | Reduced operational expenditure
|  |  | Establish a panel of legal practitioners with a fee structure; | In-house | In-house | NCR/Director: Corporate Services | 2026-01-01 | 30/04/2026 | No new irregular appointments of law firms | Approved tender award of panel of legal practitioners | Reduced operational expenditure
|  |  | All outstanding invoices for legal services rendered be subjected to taxation before payment; | In-house | In-house | NCR/Director: Corporate Services | 2026-01-01 | Monthly | Value for money and payment for services rendered | Taxed Invoices by the Taxing Master | Reduced operational expenditure
|  |  | Declare Fruitless and Wasteful expenditure incurred through intra-litigation between councillors in the UIF&W expenditure register and between the Municipal Manager and certain political office-bearers. | In-house | In-house | NCR/Director: Corporate Services | 2026-01-01 | 31/01/2026 | Fruitless and Wasteful expenditure declared | Updated UIF&W expenditure register | Reduce operational expenditure
4 | POWERS AND FUNCTIONS | The municipality conducts the following unfunded mandates: Libraries due to inadequate mandate agreement with specific reference to financial impact and related funding Department of SRAC funds directly for the provisions of library services Four staff members in library services funded by the municipality to the value of R1 768 361.36 Services in buildings owed by the municipality used for five libraries is paid by the municipality the amount of which remains undetermined. The municipality performs vehicle registration services as well as processing the renewal of licenses and permits on behalf of the department of transport. Traffic services through SLA providing for 80/20% sharing of revenue Revenue for 2024/25: R37 414 833.73 RTMC fee; R211 246.00 80% of province: R29 762 870.18 20% municipality: R7 440 717.55 Total operating expenditure: R4 119 629.62 Total operation costs: R24 754 303.32 Underfunding to the Value of R17 313 585.77 Ngaka Modiri Molema District is the Water Services authority Section 78 not done by the District as a consequent to taking over the function occasioned by the Court Order Unfunded mandate for operational costs, e.g., salaries for 128 staff members and tankering services MOU between municipality and District inadequate and does not addressing the funding of the 128 staff members alternatively transferring of water services provision with the said staff as a going concern to the District. No business plan to implement the MOU occasioned by the Court judgement | Renegotiate funding to cover all municipality’s operational costs including costs for services rendered to the libraries and operational staff | In-house | SALGA | NCR/Director: Community Services | 2026-01-01 | 30/06/2026 | No irregular expenditure | Re-negotiated mandate agrrement | Reduced operational expenditure
|  |  | Determine billing for services rendered at the five libraries | In-house | In-house | NCR/CFO | 2026-01-01 | Monthly | Provincial SRAC billed for service rendered | Monthly Bills | Increase revenue
|  |  | Establish technical task team to adress all water supply related issues including renegotiation of the MOU | In-house | District muni, Magalies Water, DWS, MISA, COGSTA, PT | NCR/Head: Legal Services | 2026-01-01 | 31/01/2026 | Functional task team | Approved establishment report by NCR | Reduce operational expenditure
|  |  | Renegotiate the SLA to cover all operational costs of the municipality on licensing services to address the underfunded value of the mandate agreement | In-house | In-house | NCR/Head: Legal Services | 2026-01-01 | 30/06/2026 | No irregular expenditure | signed re-negotiated SLA | Reduce operational expenditure
|  |  | Finalise business plan for implementation of MOU between District and the local municipality on the water supply services | In-house | In-house | NCR/Director: Technical Services | 2026-01-01 | 31/03/2026 | Court Order implemented | Council approved Business plan and signed resolution | Financial benefits to be realised through improved governance efficiencies and systems with checks and balances in place
5 | CONTRACT MANAGEMENT | Contract register last updated FY2022/23 and for the FY 2023/24 and FY2024/25 it is empty All contracts on the contract register have expired and all current active contracts are irregular month to month due collapsed SCM systems Contracted services are R66 314 774 and the cost against the total operating expenditure is 10% which is way above the set norms and standards No approved consultancy reduction plan in place A contract management committee was established but is not functional. A contract management framework was developed by Provincial Treasury for use by the whole district, however there is no evidence that this framework was formally adopted by council Overpayment of consultants for preparation of AFS Excessively high bill for cell phones at above R300 000 per month No Cell phone approved policy Most expensive cell phone gadgets are taken on contract Ineffective management on contract for Financial Systems SEBATA paid R180 000 per month for historical accounts before 2020 No service level agreement with SEBATA Ineffective management on contract for Prepaid Electricity Vendor Electricity Vending Contract expired but still being used for the past ten years No service level agreement with CIGI-CELL during the validity of contract No reconciliation of money collected by service provider and paid to the municipality Ineffective management on contract for Security Services Two security companies submitted invoices to the value of R1 500 000 per month Only one security company now providing services Litigation by one security company for payment of service rendered R16 020 763.03 Municipality does not compile monthly performance monitoring reports on contracts No audit trail of authorization of certain contract extensions and instances where contract extensions were approved accordingly | Establishment of contracts management committee | In-house | In-house | NCR/CFO | 2026-01-01 | 31/01/2026 | Established and functional contracts management committee | Approved report by Municipal manager | Financial benefits to be realised through improved governance efficiencies and systems with checks and balances in place
|  |  | Terminate all irregular contracts | In-house | In-house | NCR/CFO | 2026-01-01 | 30/04/2026 | No irregular expenditure | Signed termination letters | Reduced operational expenditure
|  |  | Review and audit allocation of cell phones to affected councillors and staff to determine qualification thereof | In-house | In-house | NCR/Director: Corporate Services | 2026-01-01 | 31/01/2026 | Cellphones allocated on need and desirability | Audit report by the Manager: Internal Audit | Reduce operational expenditure
|  |  | Reduce the monthly expenditure on cell phones through provisional capping pending the approval of cell phone policy | In-house | In-house | NCR/Director: Corporate Services | 2026-01-01 | 31/01/2026 | Capped expenditure on cellphones | Financial statement by CFO | 50% Reduction in operational expenditure
|  |  | Reconcile all payments made to SEBATA and settle outstanding debt to secure data of the municipality | In-house | In-house | NCR/CFO | 2026-01-01 | 31/03/2026 | Reconciled payments | Reconciliation report | Reduce operational expenditure
|  |  | Audit of sales and money paid by Cigi Cell to the municipality as an electricity vending contractor | In-house | In-house | NCR/CFO | 2026-01-01 | 31/03/2026 | Audited sales and revenue received | Audit report by Manager: Internal Audit | Increase revenue
|  |  | Audit the security contract to quantify costs against deliverables including the claimed amount of R16 020 763.03 | In-house | In-house | Manager: Internal Audit | 2026-01-01 | 30/04/2026 | Audited security contract and payments made | Audit report by Manager: Internal Audit | Reduced operational expenditure
6 | UIF&W EXPENDITURE | UIF & W policy still at draft stage The municipality has not developed and implemented a UIF&W expenditure reduction plan. The municipality’s UIF & W is very high Expenditure identified: Unauthorised Expenditure for 2023/24: Zero declared 2022/23: R 281 824 404 Fruitless & Wasteful expenditure for 2023/24 was R 43 368 869 Irregular Expenditure FY2023/24: R311 million Cumulative Values Unauthorised Expenditure: R 556 381 637 Fruitless & Wasteful expenditure: R 357 663 888 Irregular Expenditure: Zero declared No investigations for unauthorized, irregular and fruitless and wasteful expenditure for the balance related to the 2022/23 financial year: Fruitless & wasteful expenditure: R314 295 019 Irregular expenditure: R409 321 811 Unauthorised expenditure: R556 381 637 Quarterly reports to the Mayor and annual reports to Council on UIF&W expenditure are not submitted and as a result no oversight is conducted over the expenditure | Develop schedule for section 32 MFMA investigations on historical and current expenditure | In-house | In-house | NCR/Director: Corporate Services | 2026-01-01 | 28/02/2026 | UIF&W expenditure investigated | Approved schedule | Financial benefits to be realised through improved governance efficiencies and systems with checks and balances in place
|  |  | Council to refer UIF&W expenditure to MPAC on a quarterly basis | In-house | In house | NCR/Speaker | 2026-01-01 | Quarterly | UIF&W expenditure referred to MPAC | Council resolution | Financial benefits to be realised through improved governance efficiencies and systems with checks and balances in place
|  |  | No new irregular expenditure | In-house | In-house | NCR/CFO | 2026-01-01 | Monthly | Reduced irregular, fruitless and wasteful expenditure | Updated UIF&W expenditure register | Financial benefits to be realised through improved governance efficiencies and systems with checks and balances in place
7 | IMMOVABLE PROPERTY MANAGEMENT | Investment properties amount to R122 852 004 million Annual revenue amount to R1 million The municipality cannot account for all its immovable property portfolio due to poor asset management practices. The municipality does not have an updated register of leased assets and the immovable property portfolio. Rentals are deducted from salaries at 6% of the employee salary which is way below market related rentals There are 69 lease agreements most of which have long expired Two 99-year leases for Golf clubs at R1-00 per annum and one for animal resort at 10 Cent per annum. Others for 99 years at R2-00 per annum One Rugby Club for 25 years at R10-00 per annum Nineteen 9-year leases at rentals ranging at R1-00, R10-00, R480-00, R500, R120-00, R1000-00 per annum respectively One contract for 40 years at R10 Cent per annum Some lease agreements are on a month-to-month basis at R100-00 per month and some at R10-00 and R60-00 per annum Municipality owns five halls that are derelict or dilapidated due lack of maintenance and inadequate security Lack of immovable property management systems and standard operating procedures | Review all valid lease agreements based on determined valuations to provide for market related rentals; | In-house | In-house | NCR/Director: Community Services | 2026-01-01 | 30/08/2026 | Collection of market related rentals | Signed reviewed lease agreements | Increase revenue
|  |  | Monthly reports on billed rentals and revenue collected; | In-house | In-house | NCR/CFO | 2026-01-01 | Monthly | Maximum collection of rentals | Billing and financial statement | Increased revenue
|  |  | Develop procurement process plan for all leases that have expired; | In-house | In -house | NCR/CFO | 2026-01-01 | 30/04/2026 | Legislative compliance | Approved procurement process plan | Increase revenue
|  |  | Develop maintenance programme for Council owned facilities including the five halls. | In-house | In-house | NCR/Director: Community Services | 2026-01-01 | 31/03/2026 | Maintenance programme in place | Approved maintenance programme | Increase revenue
8 | BY LAWS AND ENFORCEMENT | Most By laws are currently at draft stage and therefore there is no enforcement leading to Lawlessness, decline in revenue collection, infrastructure vandalism, illegal electricity and water connections, illegal dumping and decline in cleanliness and health hazards, and Illegal land use rights and related loss of revenue Investment repulsion and disinvestment with material impact on the socio-economic conditions in the jurisdiction area of municipality | Approval of process plan for development of financial management by-laws and service delivery by-laws | In-house | In-house | NCR/Director: Corporate Services | 2026-01-01 | 30/04/2025 | By-law process plan in place | Appoved process plan | Financial benefits to be realised through improved governance efficiencies and systems with checks and balances in place
9 | ICT | Communication Technology policy framework (MCGICTPF) has not been approved and adopted by Council No ICT security policy approved exposing the municipality to cyber-attacks, data breaches, financial losses and legal and reputational damage, and poor access control No ICT steering committee The IT environment has weak internal controls as a result no IT risk and control assessments have been performed to ensure safety and integrity of information, employees use of their own IT equipment (laptops and gmails) and do not have corporate emails exposing the Municipality to cybercrime. There is no policy governing user access control in draft form leading to ineffective User access management There is no formal access request documentation being completed for registering users, changing access rights, password resets and termination of access on all financial / performance information systems) Municipality does not have an approved backup and retention strategy or a disaster recovery plan in place Lack of funding to invest in appropriate ICT infrastructure SAGE evolution system in place with different modules which are not adequately applied by line departments due to system incompatibility and lack of training | Approval of the ICT policy framework, user access management policy and security policy | In-house | In-house | NCR/ICT Manager | 2026-01-01 | 31/03/2026 | ICT Policy Framework in place | Approved ICT Policy Framework | Financial benefits to be realised through improved governance efficiencies and systems with checks and balances in place
|  |  | Establish ICT steering committee | In-house | In-house | NCR/ICT Manager | 2026-01-01 |  | Steering committee established and functional | Approved on establishment of ICT steering committee | Financial benefits to be realised through improved governance efficiencies and systems with checks and balances in place
|  |  | Conduct ICT risk and control assessment | In-house | In-house | NCR/ICT Manager | 2026-01-01 |  | Risk and control assessment conducted | ICT risk and control assessment reports | Financial benefits to be realised through improved governance efficiencies and systems with checks and balances in place
|  |  | Secure data storage, backup and recovery solutions | In-house | In-house | NCR/ICT Manager | 2026-01-01 |  | Secured data and information | Completion certificate | Financial benefits to be realised through improved governance efficiencies and systems with checks and balances in place
10 | AUDIT ACTION PLANS | Inadequate implementation of the audit action plan and slow response Stagnation in unfavourable disclaimer of opinion outcomes with material findings on predetermined objectives and compliance with laws and regulations. Non submission of information and supporting documents The municipality has an audit plan in place however, however there is slow movement in the progress of addressing the misstatements and other findings identified by AGSA No oversight over the preparation and implementation of the PAAP Inadequate skills capacity in Finance Directorate to prepare proper annual financial statements The audit committee and internal audit functions lack initiative and skill in handling the audit action plan. | Review the Post Audit Action Plan to ensure SMART compliance and identification of priorities that will improve annual audit outcomes | In-house | In-house | CFO | 2026-01-01 | 31/04/2026 | Updated and informed PAAP | Updated PAAP | Financial benefits to be realised through improved governance efficiencies and systems with checks and balances in place
|  |  | Quarterly progress reporting to Audit committee and Council on addressing the findings of the Auditor-General | In-house | In-house | CFO | 2026-01-01 | Quarterly | Period Coucil oversight | Approved quarterly reports and signed resolution | Financial benefits to be realised through improved governance efficiencies and systems with checks and balances in place
PILLAR FOUR: INSTITUTIONAL AND ORGANISATIONAL DEVELOPMENT
1 | OPERATING MODEL | The review of the operating model has not been conducted. Over-reliance on contractors The municipality has two satellite offices and the central office. The municipality signed the MOU with NMMDM for the provision of water services | Document the current operating model, its weaknesses, and strengths. | internal | Cogta | MM | 2026-01-01 | 2026-06-01 | Documented current operating model with its strength and weaknesses | Management report on the current documented operating model | Financial benefits to be realised through improved institutional efficiencies and systems with checks and balances in place
|  |  | Determine and audit the current human capital for the satellite office. | internal | Internal | Director: HR | 2026-01-01 | 2026-06-26 | Approved staff establishment for regional services and the list of employees placed at satellite offices | Management report on the capacity of the satellite offices
2 | ORGANISATIONAL STRUCTURE | The municipal council approved the revised organizational structure during its May 2025 meeting. However, the structure is unfunded and bloated; The current structure was costed at R296 million with 724 employees, while the new proposed structure is projected to cost R300 million with 836 employees. The migration and placement policy has been agreed upon, and consultation with labour has been finalized for implementing the new structure. Job evaluation has not been conducted DLM still utilises the Van der Merwe system of Job evaluation. Job descriptions are not yet finalised; only the manager's job descriptions are completed. | Populate the organisational structure through migration and placement of employees. | internal | NCR | NCR | 2026-01-01 | 2026-03-26 | Establish the placement comitte and its appeal commitee Placement of all employees in the approved organizational structure | Management report on the placement of employees NRC/ management report on the placement of staff | Financial benefits to be realised through improved institutional efficiencies and systems with checks and balances in place
3 | EMPLOYEE COST | Employee-related costs are the primary cost driver of operating expenditure, accounting for 50% of total OPEX, exceeding the norm of 25-40% as per Treasury Circular 71. Excessive overtime expenditure cannot be justified, as the municipality's controls are insufficient. 40 hours of overtime as per the BCEA, reduced to 20 hours as part of the cost containment strategy. The total incurred overtime expenses for the 2024/25 financial year are R24 619 792 million, and the June 2025 costs are R2 037 532. The actual employee costs remain at R338.6 million. The segregation of roles between Finance, Payroll, and HR Payroll needs to be clarified, as there are overlapping areas of concern. Annual salary increases approved for 2024/25 for all employees. Councillors also submitted upper limit salaries to the MEC, awaiting concurrence from Cogta. 3rd party payments are not up-to-date for 11 months to the value of R68 million Only medical aid paid up to 1 month in areas (September in areas) NO guarantees for salary payment for Nov and Dec 2025 due to insufficient budget, since all salaries are dependent on the equitable share Leave management controls are insufficient and pose a risk in the management of the leave system and employee leave balances. | Develop overtime SOP and manage job orders for overtime, including pre-approval of overtime work. | internal | Internal | MM /CFO | 2026-01-01 | 2026-03-26 | Approved SOP on overtime job orders and pre-approval of overtime | Approved SOP on overtime | Employee Cost: <45 per cent of OPEX (10 per cent reduction). 25 per cent reduction in overtime 92,5% on total REM). Councillor REM: 100 per cent per Gazetted maximums, subject to FRP Progress
|  |  | Reduction of overtime costs by March 2026 across all departments. | internal | Internal | MM/HOD's | 2026-01-01 | 2026-03-01 | Reduced overtime costs | Management report on overtime expenditures | 25% reduction of overtime by march 2026
|  |  | Maintain the current collective agreements on salary increases and request exemption for next round of salary negotiations | internal | Internal | NCR/MM | 2026-01-01 | 2026-07-26 | Maintain the current collective agreements on salary increases and request exemption for next round of salary negotiations | Maintain the current collective agreements on salary increases and request exemption for next round of salary negotiations | Financial benefits to be realised through improved institutional efficiencies and systems with checks and balances in place
|  |  | Develop SOP for the payroll function | internal | Internal | Director: HR | 2026-01-01 | 2026-01-26 | SOP on the payroll functions between HR and Finance | Management report on segregation of payroll between HR and Finance | Financial benefits to be realised through improved institutional efficiencies and systems with checks and balances in place
|  |  | Seek consensus from the Cogta on the implementation of upper limits | internal | Internal | NCR/MM | 2026-01-01 | 2026-01-31 | Seek consensus from the Cogta on the implementation of upper limits | Seek consensus from the Cogta on the implementation of upper limits | Financial benefits to be realised through improved institutional efficiencies and systems with checks and balances in place
|  |  | Savings from non-increases in salaries should be used to pay for 3rd party areas | internal | Internal | NCR/MM/CFO | 2026-01-01 | 2026-03-31 | Identify a funding plan to reduce the 3rd party areas | Management report on the reduction of 3rd party payment
|  |  | Keep all medical aid contributions up-to-date | internal | Internal | NCR/MM/CFO | 2026-01-01 | 2026-02-28 | Identify a funding plan to updated the medical aid payments | Management report on medical aid areas
|  |  | Negotiate with the National Treasury and National Cogta for payment relief and support | internal | National Cogta/national treasury | NCR/MM/CFO | 2026-01-01 | 2026-01-31 | Guarantees on payment of salaries issued | Management report on guarantees of payment of salaries
|  |  | Develop SOP for leave management. | internal | Internal | Director: HR | 2026-01-01 | 2026-03-31 | SOP on the management and administrative of leave | Management report on leave management
|  |  | Use the Sage leave management module. | internal | Internal | Director: HR / ICT manager | 2026-01-01 | 2026-02-28 | Fully system utilization of the leave module on Sage | System report on leave | Financial benefits to be realised through improved institutional efficiencies and systems with checks and balances in place
4 | FILLING OF CRITICAL VACANCIES | All senior management positions remain vacant. Parallel Appointment of officials in similar positions. Irregular employment practices. Lack of vacancy prioritization in line with the affordability ratio of the municipality. The council approved the appointment of 70 additional temporary workers in July 2025; however, they were terminated due to financial constraints. Family-related appointments. Irregular appointment in acting positions and exceeded the regulated acting period of 3 months. High Vacancy Rate in Management Levels at 90%. There is a high vacancy rate in all technical services areas. (Electricity, Water, Sanitation, and Roads) | Advertise all senior management posts/ or request secondment from National Cogta/ National Treasury | internal | NCR | NCR/MM | 2026-01-01 | 2026-03-31 | Letters of appointed HOD's or Seconded personnel | Letters of appointment or secondment | Financial benefits to be realised through improved institutional efficiencies and systems with checks and balances in place
|  |  | Terminate or offer alternative positions to affected managers. | internal | Internal | NCR/MM | 2026-01-01 | 2026-02-28 | Termination letters or letters of placement in alternative posts | Termination letters and placement Lettes to alternative posts | Financial benefits to be realised through improved institutional efficiencies and systems with checks and balances in place
|  |  | Identify new critical vacancies in the organizational structure | internal | Internal | NCR/MM | 2026-01-01 | 2026-03-31 | List of critical vacant positions with funding plan | Management report on vacant position , identified as critical/ core and essential and funding plan | Financial benefits to be realised through improved institutional efficiencies and systems with checks and balances in place
|  |  | Terminate all temporary positions in line with budgetary constraints | internal | Internal | NCR/MM | 2026-01-01 | 2026-02-28 | Letters of termination | Letters of termination | Financial benefits to be realised through improved institutional efficiencies and systems with checks and balances in place
|  |  | Determine the need for acting and request an apply for exemption from the acting policy for long-term acting arrangements. | internal | internal | NCR/MM | 2026-01-01 | 2026-02-28 | Identify all positions to be filled through acting arrangements in line with municipal staff regulations | Management report on acting arrangements | Financial benefits to be realised through improved institutional efficiencies and systems with checks and balances in place
5 | STAFF VERIFICATION AND QUALIFICATION AUDIT | The employee verification exercise was conducted but not completed. To date, 40 employees have not been verified. The payroll audit was not conclusive and remains outstanding. | Conduct a new staff audit ias well as payroll audit in preparation for the impending placement process. | internal | Internal | NCR/ MM | 2026-01-01 | 2026-02-28 | List of all employees in the staff establishment ageist the organizational structure positions | Management report on the results of the staff verification Management report on the results of the payroll | Financial benefits to be realised through improved institutional efficiencies and systems with checks and balances in place
6 | STAFF DISCIPLINE | Code of conduct not enforced. Three employees were charged with fraud for transacting in the municipal account without the authorization of the municipal manager. The employees were found guilty. Ten employees were charged with misconduct, malicious damage to property, and violent behaviour. The suspensions of senior management members, including the Chief Financial Officer, the Director of Corporate Services, and the acting Municipal Manager and PMU Manager, resulted in instability and a lack of accountability. Manager for water services on prolonged sick leave The ethical behaviour of employees and the code of conduct were not efficiently managed. Dereliction of duty by Managers and employees. Sporadic incidents of crime were also reported in DLM (e.g., holding people hostage, riots, kidnappings, etc.) No municipality can function in a chaotic and unsafe environment. | Provide the detailed sanctions for the three employees charged with operating the municipal bank account | internal | Internal | Director: HR | 2026-01-01 | 2026-03-31 | Detailed sanctions of all employees who are charged with illegally operated municipal account | Management report on the disciplinary process and its sanctions muted again employees who are charged with operating illegally the municipal account | Financial benefits to be realised through improved institutional efficiencies and systems with checks and balances in place
|  |  | Provide detailed sanction on employees charged with malicious damage to property | internal | Internal | Director: HR | 2026-01-01 | 2026-03-31 | Detailed sanctions of all employees charged with malicious to property | Management report on the disciplinary process and its sanctions muted against employees | Financial benefits to be realised through improved institutional efficiencies and systems with checks and balances in place
|  |  | Provide letters of intention to suspend and reasons why matters are not resolved to date. | internal | Internal | Director:HR | 2026-01-01 | 2026-03-31 | Provide reasons for suspicions of all employees and recall or finalise the disciplinary cases | Management report on all suspended officials and the status of their respective cases | Financial benefits to be realised through improved institutional efficiencies and systems with checks and balances in place
|  |  | Implement the sick leave policy and its conditions | internal | Internal | Director: HR | 2026-01-01 | 2026-03-31 | Implement the approved leave policy | Management report on the leave policy provisions of sick leave | Financial benefits to be realised through improved institutional efficiencies and systems with checks and balances in place
|  |  | Provide a team-building session for all managers | internal | Internal | Director | 2026-01-01 | 2026-06-30 | Provide training on ethics and organizational culture | Management report on ethics and organizational culture training | Financial benefits to be realised through improved institutional efficiencies and systems with checks and balances in place
7 | CONSEQUENCE MANAGEMENT | There is a general disregard for compliance with key legislation, with no consequences for transgressions. No updated consequence management policies. | Enforce consequence management policy | internal | Internal | NCR/MM | 2026-01-01 | 2026-06-30 | Training program for staff on code of conduct | Rraining program on code of conduct | Financial benefits to be realised through improved institutional efficiencies and systems with checks and balances in place
8 | PERFORMANCE MANAGEMENT | The municipality lacks approved internal policies and procedures to manage the collection, recording, processing, monitoring, and reporting of performance information. The majority of the indicators are not well-defined, and inconsistencies between the SDBIP and APP limit the testing of the reliability of the performance indicators and their related targets. The lack of effective records management has been the primary cause of the repeated disclaimers of opinions on performance information issued by the AGSA over the past three consecutive financial years. PMS is not cascaded to staff below S56/57 managers. | Develop SOP for the implementation of the performance management framework | internal | Cogta | NCR/MM | 2026-01-01 | 2026-06-30 | Approved SOP on the management of performance reporting and information. Including its file plan and records procedures | Management report on the alignment of all performance reports and information for reporting | Financial benefits to be realised through improved institutional efficiencies and systems with checks and balances in place
9 | HR STRATEGY | The Municipality does not have an approved HR Strategy to support its operations. | Identify value drivers for HR strategy 2026-2030 | internal | NCR | NCR/Director HR | 2026-01-01 | 2026-06-30 | Approved HR strategy | Approved HR strategy | Financial benefits to be realised through improved institutional efficiencies and systems with checks and balances in place
10 | KEY HR POLICIES | The municipality fails to properly implement approved Policies. The municipality is in contravention of the Occupational Health and Safety Act, as most of its buildings are not conducive to a productive organisation. The Department of Labour has already issued a contravention notice to the site offices of the municipality | Develop SOP for the implementation of Policies | internal | NCR | Director : HR | 2026-01-01 | 2026-06-30 | Developed SOP on the implementation of policies | Management report on the application of HR policies | Financial benefits to be realised through improved institutional efficiencies and systems with checks and balances in place
|  |  | Conduct a compliance audit for all municipal buildings on OHS Act. | internal | NCR | Director: HR | 2026-01-01 | 2026-03-31 | Report on the compliance audit for all building of the municipality | Compliance report on all buildings of the municipality for the OHS Act. | Financial benefits to be realised through improved institutional efficiencies and systems with checks and balances in place
11 | SKILLS AND COMPETENCIES | The municipality lacks skilled employees in critical operational functions within service delivery and corporate support. Lack of critical skills in Finance departments (procurement, AFS, Revenue management, and Expenditure management. Lack of Skills in all Technical services (Electricity, Water, Waste management, and Roads). No employee development plans. Cogta conducted a qualification and skills audit; however, it did not include all employees. The Skills Development plan has been approved and submitted to the SETA | Conduct skills gap analysis across the department as part of the Workplace Skills Plan across all functional areas. | internal | Cogta | NCR/MM | 2026-01-01 | 2026-06-30 | Report on skills audit | Management report and findings on skills audit | Financial benefits to be realised through improved institutional efficiencies and systems with checks and balances in place
12 | CHANGE MANAGEMENT | The municipality lacks internal capacity to manage change. The psychological effect of non-payment of salaries has affected employee morale and trust. The 3rd-party payment areas have created an unfavourable environment for employee relations. Unethical behaviour observed through employee grievances Politicised administration. Employee personal differences compromise professional relationships. The culture in DLM is not conducive to creating an effective and efficient municipality. Impunity, disregard for legislation, rules, processes, etc, have been raised as concerns | Inform employees of the implications for 3rd part payment areas | internal | Internal | NCR/MM | 2026-01-01 | 2026-02-28 | Advisory memo to all employees on 3rd party payments | Management report on the communication letters issued to employees | Financial benefits to be realised through improved institutional efficiencies and systems with checks and balances in place
|  |  | Define the expectation of the new culture, values, and ethical behaviour | internal | Internal | NCR/MM | 2026-01-01 | 2026-03-31 | Introduction of change management interventions | Management report on change interventions | Financial benefits to be realised through improved institutional efficiencies and systems with checks and balances in place
13 | RECORDS MANAGEMENT | The municipality lacks a proper system to ensure the safekeeping of documentation that supports its financial statements and annual performance report. There is no record management policy, system, or procedure. Document management is lacking across all departments. Employees' records and system exist, but are not updated. The employee leave records management system is dysfunctional (manual forms are transferred into the system). The leave management policy is not being adhered to in some departments. Leave audit not done. The SAGE Electronic System is operational, but not optimised by the municipality. | Develop the record management policy and file plan | internal | Internal | Manager records management | 2026-01-01 | 2026-03-31 | Approved records management policy and file plan | Approved records management policy and file plan | Financial benefits to be realised through improved institutional efficiencies and systems with checks and balances in place
|  |  | Establish the SOP for record management | internal | Internal | Manager records management | 2026-01-01 | 2026-03-31 | Approved SOP for records management | Approved records management policy SOP
|  |  | Establish employee records management SOP. | internal | Internal | Director: HR | 2026-01-01 | 2026-03-31 | Approved SOP for employee records | SOP for employee records
|  |  | Optimize the electronic leave records management | internal | Internal | Director:HR | 2026-01-01 | 2026/06/31 | Utilize the Sage leave module | Utilization report for the sage leave module
|  |  | Enforce leave management policy | internal | Internal | Director:HR | 2026-01-01 | 2026-02-28 | Enforce leave policy | Management report of leave

## Phase 2 Stabilisation
DITSOBOTLA LOCAL MUNICIPALITY
PHASE 2: STABILISATION
NO | FOCUS AREA | KEY ASSESSMENT FINDING (BASELINE) | KEY ACTIVITIES | RESOURCES REQUIRED | RESOURCES MOBILISED | RESPONSIBLE | START DATE | END DATE | KEY PERFORMANCE INDICATOR | PoE | BUDGET PARAMETER/ REVENUE TARGET/ SPENDING LIMIT | MUNICIPAL PROGRESS REPORT
[12 empty] | STEPS TAKEN | PROGRESS MADE | FINANCIAL IMPACT | OTHER NOTEWORTHY DEVELOPMENTS
PILLAR ONE: GOOD GOVERNANCE
1 | Governance Model (Council and Sect. 79 & 80 Committees) | Municipal Council not sitting to date for the financial year 2025/26 except for the special meeting held for the election of the Speaker and Mayor The municipality’s council and its committees are not yet functional. Rules and Orders outdated Resolutions register or a system to track resolutions not updated The code of conduct that addresses ethical behavior by councillors is not implemented. Councillors in arrears for service provided and rates in the amount of R1.1 million Staff in arrears for services provided and rates in the amount of R13 million Lack of policies and systems in place to enforce Code of Conduct No consequence management against councillors and staff in arrears Non-compliance and failure to fulfil the Constitutional obligations Economic decline and high unemployment rates Committees of council do not quorate due to non-attendance of meetings by councillors There is no record of councillors’ declaration of interest. There is Political Interference and free for all in recruitment process of staff and SCM functions Non-compliance with statutory prescripts Forensic investigations conducted into allegations of Maladministration, Fraud and Corruption Investigations reports cannot be located No evidence that the recommendations of the investigations were implemented Insecure and unsafe working environment. Council has not approved and implemented a stakeholder engagement strategy and public participation policy although the draft is in place awaiting Council approval Non approval and Failure to timeously prepare and process statutory reports i.e. Section 71, Section 52(b) and (b) MFMA Reports, AFS, Annual reports, SCM Regulation 6 Reports and Section 32 investigation Reports Section 71 MFMA Report not approved in line with calendar of Council Ward committees not functional and ward committee operational plans not provided | Quarterly reporting to Council on nonattendance of Council and committee meetings, and enforcement of Code of Conduct for councillors | In-house | In house | NCR/Manager: Office of Speaker | 2027-01-01 | Quarterly | Fully functional council and committees | Council approved reports and sugned resolutions | Financial benefits to be realised through improved governance efficiencies and systems with checks and balances in place
|  |  | Maintain an updated Council resolutions register | In-house | In-house | NCR/Manager: Office of Speaker | 2027-01-01 | Quarterly | Council resolutions implemented | Updated Register | Financial benefits to be realised through improved governance efficiencies and systems with checks and balances in place
|  |  | Quarterly reporting progress of Council resolutions; | In-house | In-house | NCR/Director: Corporate Services | 2027-01-01 | Quarterly | Council resolutions implemented | Council approved reports and sugned resolutions | Financial benefits to be realised through improved governance efficiencies and systems with checks and balances in place
|  |  | Recover any arrears not settled at end of the current Council Term of councillors’ pension fund and or Ex Gratia payment through claims before payment; | In-house | In-house | NCR/Director: Corporate Services | 2027-01-01 | End of current term | Zero arrears owed by councillors | Financial Report by CFO | Increase revenue
|  |  | Recover 25% monthly from each staff member through payroll deductions and payment arrangements and include honouring of current accounts; | In-house | In-house | NCR/Director: Corporate Services | 2027-01-01 | Monthly | Reduction of arrears for staff | Financial Report by CFO | Increase revenue
|  |  | Quarterly reporting to Council on payment for services by councillors and staff; | In-house | In-house | NCR/Director: Corporate Services | 2027-01-01 | Quarterly | Honouring of accounts payment for councillors and staff | Council approved reports and sugned resolutions | Increase revenue
|  |  | Timeous approval of all statutory reports in line with the calendar | In-house | PT | NCR/CFO | 2026-01-01 | Alignment with Calendar/MFMA compliace Register | Legislative compliance | Approved statutory reports | Financial benefits to be realised through improved governance efficiencies and systems with checks and balances in place
|  |  | Approval of policy frameworks to improve on enforcement of Code of Conduct for councillors; | In-house | In-house | NCR/Director: Corporate Services | 2027-01-01 | 31/03/2027 | Code of conduct for councillors enforced | Council approved reports and sugned resolutions | Financial benefits to be realised through improved governance efficiencies and systems with checks and balances in place
|  |  | Annual declaration of interests by councillors and staff; | In-house | In-house | NCR/Director: Corporate Services | 2027-01-01 | Annually | Interests declared | Updated Declarations Register | Financial benefits to be realised through improved governance efficiencies and systems with checks and balances in place
|  |  | All councillors to sign a pledge on compliance with the Code of Conduct and adherence to the roles and responsibilities | In-house | In-house | NCR/Director: Corporate Services | 2027-01-01 | 31 /01/2027 | Pledge signed | Signed pledges | Financial benefits to be realised through improved governance efficiencies and systems with checks and balances in place
|  |  | Review the Rules and Orders; | In-house | SALGA | NCR/Director: Corporate Services | 2027-01-01 | 31/03/2027 | Rules and Orders in place to regulate order of business of Council | Council approved report and signed resolution | Financial benefits to be realised through improved governance efficiencies and systems with checks and balances in place
|  |  | Implement the recommendations of the forensic investigations through disciplinary process, recover losses and referral for criminal investigations; | In-house | SIU | NCR/MM | 2027-01-01 | Monthly | Improved accountability and good governance practices | Approved progress report on implementation | Financial benefits to be realised through improved governance efficiencies and systems with checks and balances in place
|  |  | Implement the recommendations of the SIU investigations through disciplinary process, recoveries of moneys lost and referral for criminal investigations; | In-house | SIU | NCR/MM | 2027-01-01 | Monthly | Improved accountability and good governance practices | Approved progress report on implementation | Financial benefits to be realised through improved governance efficiencies and systems with checks and balances in place
2 | SYSTEM OF DELEGATION | No approved system of delegations by the municipal Council leading to administrative and operational inefficiencies, no checks and balances, irregular and unlawful decisions and non-compliance with statutory prescripts No sub-delegation of authority to staff leading to Staff executing work without delegated authority No delegation register Selective acceptance of sourced external legal opinions based on personal interest | Review and approval of the system of delegation | In-house | SALGA/COGTA | NCR/Director: Corporate Services | 2027-01-01 | 31/03/2027 | Systems in place | Council approved report and signed resolution | Financial benefits to be realised through improved governance efficiencies and systems with checks and balances in place
|  |  | Maintain updated delegations register | In-house | In-house | NCR/Director: Corporate Services | 2027-01-01 | Quarterly | Improved accountability and good governance practices | Updated Delegations Register | Financial benefits to be realised through improved governance efficiencies and systems with checks and balances in place
|  |  | Municipal manager to ensure sub-delegations of powers and functions to the lowest possible official to maximise operational and administrative efficiencies | In-house | In-house | NCR/Director: Corporate Services | 2027-01-01 | 30/04/2027 | Maximised administrative and operational efficiencies | Signed sub-delegations | Financial benefits to be realised through improved governance efficiencies and systems with checks and balances in place
3 | LITIGATION AND CONTINGENT LIABILITY | The municipality has a huge contingent liability potential exposure of about R63 770 076.34 million No litigation strategy in place No delegated authority to initiate and oppose litigation for or against the municipality Irregular and unlawful decisions by structures, executive and the administration due to inadequate legal advice/support. No updated litigation register Default judgements leading to Writs of Execution, Attachment of assets, Attachment of bank accounts and equitable shares Failure to honour settlement agreements with law firms for services rendered Lack of instructions on Court applications from Finance Directorate Legal fees paid by the Municipality to service providers in respect of legal services during the: • 2022/23 financial year were R 5 020 401.06 million. Budget 2022/23 FY: R3.2 million • 2023/24 financial year were R 1 310 345.26 million. Budget 2023/24: R3.2 million • 2024/25 financial year were R16 530 997.22 Budget 2024/25 FY; R3.6 million • 2025/26 financial year (First two months) R7 648 593.90 • Budget 2025/26 FY: R3.6 million Invoice processing systems with checks and balances and payment validation collapsed Law firms submitting invoices where there is no (or minimal) paper trail to confirm services rendered Outstanding invoices to the value of R5 213 316.40 No records of work done Fruitless and Wasteful intra-institutional litigation against councillors by other councillors and between Municipal manager against the political office bearers of the municipality Costs awarded in the personal capacity from councillors not collected | Develop standard operating procedure for approach to new Court applications against the municipality; | In-house | In-house | NCR/Director: Corporate Services | 2027-01-01 | 31/03/2027 | Effective litigation management | Approved SOP's | Financial benefits to be realised through improved governance efficiencies and systems with checks and balances in place
|  |  | All payments for legal invoices for the past five years to date of approval of the national intervention FRP by Minister of Finance be audited by an independent entity appointed by the National Treasury; | In-house | In-house | NCR/Director: Corporate Services | 2027-01-01 | 30/06/2027 | Improved accountability and good governance practices | Audit Report | Financial benefits to be realised through improved governance efficiencies and systems with checks and balances in place
|  |  | Implementation of renegotiated settlement agreements with law firms for invoices; | In-house | In-house | NCR/Director: Corporate Services | 2027-01-01 | Monthly | Improved accountability and good governance practices | Payments made/Financial Report by CFO | Financial benefits to be realised through improved governance efficiencies and systems with checks and balances in place
|  |  | Develop and implement invoice processing control system; | In-house | In-house | NCR/Director: Corporate Services | 2027-01-01 | Monthly | Improved accountability and good governance practices | No new unauthorised expenditure on legal costs/Reduction in legal costs | Financial benefits to be realised through improved governance efficiencies and systems with checks and balances in place
|  |  | All outstanding invoices for legal services rendered be subjected to taxation before payment; | In-house | In-house | NCR/Director: Corporate Services | 2027-01-01 | 30/09/2027 | Improved accountability and good governance practices | Taxed invoices before payment | Reduce operational expenditure
4 | POWERS AND FUNCTIONS | The municipality conducts the following unfunded mandates: Libraries due to inadequate mandate agreement with specific reference to financial impact and related funding Department of SRAC funds directly for the provisions of library services Four staff members in library services funded by the municipality to the value of R1 768 361.36 Services in buildings owed by the municipality used for five libraries is paid by the municipality the amount of which remains undetermined. The municipality performs vehicle registration services as well as processing the renewal of licenses and permits on behalf of the department of transport. Traffic services through SLA providing for 80/20% sharing of revenue Revenue for 2024/25: R37 414 833.73 RTMC fee; R211 246.00 80% of province: R29 762 870.18 20% municipality: R7 440 717.55 Total operating expenditure: R4 119 629.62 Total operation costs: R24 754 303.32 Underfunding to the Value of R17 313 585.77 Ngaka Modiri Molema District is the Water Services authority Section 78 not done by the District as a consequent to taking over the function occasioned by the Court Order Unfunded mandate for operational costs, e.g., salaries for 128 staff members and tankering services MOU between municipality and District inadequate and does not addressing the funding of the 128 staff members alternatively transferring of water services provision with the said staff as a going concern to the District. No business plan to implement the MOU occasioned by the Court judgement | Implement the renegotiated SLA for licencing services | In-house | In-house | NCR/Director: Community Services | 2027-01-01 | Monthly | No subsidisation | Financial report by CFO | Reduce operational expenditure
|  |  | Implement the renegotiated mandate agreement for library services | In-house | In-house | NCR/Director: Community Services | 2027-01-01 | Monthly | No subsidisation | Financial report by CFO | Reduce operational expenditure
|  |  | Monthly billing of the provincial SRAC for services rendered at five library services | In-house | In-house | NCR/CFO | 2027-01-01 | Monthly | Billing issued | Financial report by CFO | Increase revenue
|  |  | Implement the renegotiated MOU for water supply services | In-house | In-house | NCR/Director: Technical services | 2027-01-01 | Monthly | No subsidisation | Financial report by CFO | Reduce operational expenditure
5 | CONTRACT MANAGEMENT | Contract register last updated FY2022/23 and for the FY 2023/24 and FY2024/25 it is empty All contracts on the contract register have expired and all current active contracts are irregular month to month due collapsed SCM systems Contracted services are R66 314 774 and the cost against the total operating expenditure is 10% which is way above the set norms and standards No approved consultancy reduction plan in place A contract management committee was established but is not functional. A contract management framework was developed by Provincial Treasury for use by the whole district, however there is no evidence that this framework was formally adopted by council Overpayment of consultants for preparation of AFS Excessively high bill for cell phones at above R300 000 per month No Cell phone approved policy Most expensive cell phone gadgets are taken on contract Ineffective management on contract for Financial Systems SEBATA paid R180 000 per month for historical accounts before 2020 No service level agreement with SEBATA Ineffective management on contract for Prepaid Electricity Vendor Electricity Vending Contract expired but still being used for the past ten years No service level agreement with CIGI-CELL during the validity of contract No reconciliation of money collected by service provider and paid to the municipality Ineffective management on contract for Security Services Two security companies submitted invoices to the value of R1 500 000 per month Only one security company now providing services Litigation by one security company for payment of service rendered R16 020 763.03 Municipality does not compile monthly performance monitoring reports on contracts No audit trail of authorization of certain contract extensions and instances where contract extensions were approved accordingly | Develop and approval of contract management framework | In-house | PT | CFO | 2027-01-01 | 30/05/2027 | Contract management framework in place | Council approved reports and signed resolution | Financial benefits to be realised through improved governance efficiencies and systems with checks and balances in place
|  |  | Maintain an updated contract register | In-house | In-house | CFO | 2027-01-01 | Monthly | Legisltaive compliance | Updated Contract Register | Financial benefits to be realised through improved governance efficiencies and systems with checks and balances in place
|  |  | Develop and approve the cell phone policy | In-house | In-house | Director: Corporate Services | 2027-01-01 | 30/04/2027 | Cell phone policy in place | Council approved reports and signed resolution | Reduce operational expenditure
|  |  | Analysis and monitoring of cell phone usage by those provided with cell phones | In-house | In-house | Director: Corporate Services | 2027-01-01 | Quarterly | Analysis and monitoring taking place | Analysis and monitoring reports | Reduce operational expenditure
6 | UIF&W EXPENDITURE | UIF & W policy still at draft stage The municipality has not developed and implemented a UIF&W expenditure reduction plan. The municipality’s UIF & W is very high Expenditure identified: Unauthorised Expenditure for 2023/24: Zero declared 2022/23: R 281 824 404 Fruitless & Wasteful expenditure for 2023/24 was R 43 368 869 Irregular Expenditure FY2023/24: R311 million Cumulative Values Unauthorised Expenditure: R 556 381 637 Fruitless & Wasteful expenditure: R 357 663 888 Irregular Expenditure: Zero declared No investigations for unauthorized, irregular and fruitless and wasteful expenditure for the balance related to the 2022/23 financial year: Fruitless & wasteful expenditure: R314 295 019 Irregular expenditure: R409 321 811 Unauthorised expenditure: R556 381 637 Quarterly reports to the Mayor and annual reports to Council on UIF&W expenditure are not submitted and as a result no oversight is conducted over the expenditure | Council to approve the UIF&W expenditure policy | In-house | PT | CFO | 2027-01-01 | 31/05/2027 | UIF&W expenditure in place | Council approved reports and signed resolution | Financial benefits to be realised through improved governance efficiencies and systems with checks and balances in place
|  |  | Conduct section 32 MFMA investigations | In-house | In-house | Chairperson: MPAC | 2027-01-01 | Quarterly | Legisltive compliance and improved accountability | Council approved reports and signed resolution | Financial benefits to be realised through improved governance efficiencies and systems with checks and balances in place
|  |  | Quarterly reporting of UIF&W expenditure to the Mayor and annually to the Council | In-house | In-house | CFO | 2027-01-01 | Quarterly | Legisltive compliance and improved accountability | Council approved reports and signed resolutions | Financial benefits to be realised through improved governance efficiencies and systems with checks and balances in place
|  |  | Council to refer UIF&W expenditure to MPAC on a quarterly basis | In-house | In-house | Speaker | 2027-01-01 | Quarterly | Legisltive compliance and improved accountability | Council approved reports and signed resolutions | Financial benefits to be realised through improved governance efficiencies and systems with checks and balances in place
|  |  | Maintain an updated UIF&W expenditure register | In-house | In-house | CFO | 2027-01-01 | Quarterly | Legisltive compliance and improved accountability | Updated UIF&W expenditure register | Financial benefits to be realised through improved governance efficiencies and systems with checks and balances in place
|  |  | Approve UIF&W expenditure reduction plan; | In-house | In-house | CFO | 2027-01-01 | 30/04/2027 | Reduced UIF&W expenditure | Council approved reports and sugned resolutions | Financial benefits to be realised through improved governance efficiencies and systems with checks and balances in place
|  |  | Disciplinary Board to report quarterly to Council; | In-house | In-house | Chairperson: DB | 2027-01-01 | Quarterly | Legisltive compliance and improved accountability | Council approved reports and sugned resolutions | Financial benefits to be realised through improved governance efficiencies and systems with checks and balances in place
7 | IMMOVABLE PROPERTY MANAGEMENT | Investment properties amount to R122 852 004 million Annual revenue amount to R1 million The municipality cannot account for all its immovable property portfolio due to poor asset management practices. The municipality does not have an updated register of leased assets and the immovable property portfolio. Rentals are deducted from salaries at 6% of the employee salary which is way below market related rentals There are 69 lease agreements most of which have long expired Two 99-year leases for Golf clubs at R1-00 per annum and one for animal resort at 10 Cent per annum. Others for 99 years at R2-00 per annum One Rugby Club for 25 years at R10-00 per annum Nineteen 9-year leases at rentals ranging at R1-00, R10-00, R480-00, R500, R120-00, R1000-00 per annum respectively One contract for 40 years at R10 Cent per annum Some lease agreements are on a month-to-month basis at R100-00 per month and some at R10-00 and R60-00 per annum Municipality owns five halls that are derelict or dilapidated due lack of maintenance and inadequate security Lack of immovable property management systems and standard operating procedures | Audit of all immovable property portfolio owned by the municipality; | In-house | In-house | NCR/Director: Community Services | 2027-01-01 | 30/10/2027 | Legisltive compliance and improved accountability | Audit Report | Financial benefits to be realised through improved governance efficiencies and systems with checks and balances in place
|  |  | Maintain an updated register on leased immovable properties owned by the municipality; | In-house | In-house | NCR/Director: Community Services | 2027-01-01 | Quarterly | Legisltive compliance and improved accountability | Updated Reister on immovable property portfolio | Financial benefits to be realised through improved governance efficiencies and systems with checks and balances in place
|  |  | Monthly reports on billed rentals and revenue collected; | In-house | In-house | NCR/Director: Community Services | 2027-01-01 | Monthly | Maximum collection of rentals | Financial Report by CFO | Increase revenue
|  |  | Collection of market related rentals from tenants; | In-house | In-house | CFO | 2027-01-01 | Monthly | Maximum collection of rentals | Financial Report by CFO | Increase revenue
|  |  | Submit the alienation policy to Council for approval; | In-house | In-house | NCR/Director: Community Services | 2027-01-01 | 31/03/2027 | Legisltive compliance and improved accountability | Council approved reports and signed resolutions | Financial benefits to be realised through improved governance efficiencies and systems with checks and balances in place
|  |  | Identify strategic land parcels and explore Public-Private Partnerships; | In-house | In-house | NCR/Director: Community Services | 2027-01-01 | 30/10/2027 | New private investments | Council approved reports and signed resolutions | Financial benefits to be realised through improved governance efficiencies and systems with checks and balances in place
|  |  | Implement maintenance programme for rental stock and facilities. | In-house | In-house | NCR/Director: Community Services | 2027-01-01 | 30/11/2027 | Enhanced structural integrity | Facilities management report | Financial benefits to be realised through improved governance efficiencies and systems with checks and balances in place
|  |  | Install prepaid meters in rental stock; | In-house | In-house | NCR/Director: Community Services | 2027-01-01 | 30/06/2028 | Maximum collection for services rendered | Facilities management report | Increase revenue
|  |  | Reconcile alienation transactions with Deeds office records for the past five years up to effective date of the national mandatory FRP; | In-house | In-house | NCR/Director: Community Services | 2027-01-01 | 30/07/2027 | Legisltive compliance and improved accountability | Reconciliation report and Coucil report together with signed resolution | Financial benefits to be realised through improved governance efficiencies and systems with checks and balances in place
|  |  | Renegotiate the valid 99 year and long-term leases; | In-house | In-house | NCR/Director: Community Services | 2027-01-01 | 30/09/2027 | Re-negotiated long-term leases | signed long-term lease agreements | Increase revenue
8 | BY LAWS AND ENFORCEMENT | Most By laws are currently at draft stage and therefore there is no enforcement leading to Lawlessness, decline in revenue collection, infrastructure vandalism, illegal electricity and water connections, illegal dumping and decline in cleanliness and health hazards, and Illegal land use rights and related loss of revenue Investment repulsion and disinvestment with material impact on the socio-economic conditions in the jurisdiction area of municipality | Enforcement of promulgated by-laws | In-house | In-house | NCR/Director: Community Services | 2027-01-01 | Monthly | Restoration of law and order | Enforcement Reports | Increase revenue
|  |  | Monthly reporting on revenue generated from enforcement of by-laws | In-house | In-house | CFO | 2027-01-01 | Monthly | Maximise revenue collection | Revenue collection reports | Increase revenue
|  |  | Review and develop new by-laws prioritising financial and service delivery by-laws | In-house | In-house | Municipal Manager | 2027-01-01 | 28/02/2028 | By-laws in place | Notice of Promulgated by-laws | Financial benefits to be realised through improved governance efficiencies and systems with checks and balances in place
9 | Information and Communication Technology | Communication Technology policy framework (MCGICTPF) has not been approved and adopted by Council No ICT security policy approved exposing the municipality to cyber-attacks, data breaches, financial losses and legal and reputational damage, and poor access control No ICT steering committee The IT environment has weak internal controls as a result no IT risk and control assessments have been performed to ensure safety and integrity of information, employees use of their own IT equipment (laptops and gmails) and do not have corporate emails exposing the Municipality to cybercrime. There is no policy governing user access control in draft form leading to ineffective User access management There is no formal access request documentation being completed for registering users, changing access rights, password resets and termination of access on all financial / performance information systems) Municipality does not have an approved backup and retention strategy or a disaster recovery plan in place Lack of funding to invest in appropriate ICT infrastructure SAGE evolution system in place with different modules which are not adequately applied by line departments due to system incompatibility and lack of training | Hold quarterly meetings of ICT steering committee; | In-house | In-house | Manager: ICT | 2027-01-01 | Quarterly | Effective governance of ICT initiatives | Minutes of ICT steering committee meetings | Financial benefits to be realised through improved governance efficiencies and systems with checks and balances in place
|  |  | Periodic ICT risk and control assessments; | In-house | In-house | Manager: ICT | 2027-01-01 | Quarterly | No security breaches and data and information secured | ICT risk and control assessment reports | Financial benefits to be realised through improved governance efficiencies and systems with checks and balances in place
|  |  | Procure and implement an integrated electronic document and records management system compliant with National Archives standards when finances of the municipality stabilize; | In-house | In-house | Manager: ICT | 2027-01-01 | 30/07/2027 | Improved records management | Report of ICT Manager | Financial benefits to be realised through improved governance efficiencies and systems with checks and balances in place
|  |  | Monthly update of the website. | In-house | In-house | Manager: ICT | 2027-01-01 | Monthly | Legisltive compliance and improved accountability | Updated website | Financial benefits to be realised through improved governance efficiencies and systems with checks and balances in place
|  |  | Implement SAGE evolution modules; | In-house | In-house | Manager: ICT | 2027-01-01 | 30/09/2027 | Maximise use of technology for efficiencies | ICT Manager report | Financial benefits to be realised through improved governance efficiencies and systems with checks and balances in place
10 | AUDIT ACTION PLANS | Inadequate implementation of the audit action plan and slow response Stagnation in unfavourable disclaimer of opinion outcomes with material findings on predetermined objectives and compliance with laws and regulations. Non submission of information and supporting documents The municipality has an audit plan in place however, however there is slow movement in the progress of addressing the misstatements and other findings identified by AGSA No oversight over the preparation and implementation of the PAAP Inadequate skills capacity in Finance Directorate to prepare proper annual financial statements The audit committee and internal audit functions lack initiative and skill in handling the audit action plan. | Implement Post Audit Action Plan | In-house | In-house | CFO | 2027-01-01 | Quarterly | Improved AG audit outcomes, accountability and good governance practices | AG Audit Reports | Financial benefits to be realised through improved governance efficiencies and systems with checks and balances in place
|  |  | Quarterly progress reporting to Audit committee and Council on addressing the findings of the Auditor-General | In-house | In-house | CFO | 2027-01-01 | Quarterly | Improved AG audit outcomes, accountability and good governance practices | Council approved reports and sugned resolutions | Financial benefits to be realised through improved governance efficiencies and systems with checks and balances in place
11 | INTERNAL AUDIT | Internal Audit Unit has one staff member being the Internal Audit Manager and has two vacant positions per organisational structure. Internal audit plan not signed and the Charter has not been approved Internal audit not functional due to capacity constraints and as a result there is non-compliance with statutory prescripts The term of the Audit Committee ended on the 28 Feb 2023 as a result no oversight role is provided on financial reporting, internal controls, risk management and compliance with laws. No audit reports are submitted to Council | Approval of internal audit plan and Charter | In-house | In-house | Manager: Internal Auditor | 2027-01-01 | 31/05/2027 | Improved AG audit outcomes, accountability and good governance practices | Approved Audit Charetr and audit plan togethjer with signed resolutions | Financial benefits to be realised through improved governance efficiencies and systems with checks and balances in place
|  |  | Quarterly progress reporting on implementation of internal audit plan to Audit committee and Council | In-house | In-house | Manager: Internal Auditor | 2027-01-01 | Quarterly | Improved AG audit outcomes, accountability and good governance practices | Council approved reports and sugned resolutions | Financial benefits to be realised through improved governance efficiencies and systems with checks and balances in place
12 | RISK MANAGEMENT | There is no Chief Risk Officer (CRO) appointed as a result there is no process for risk identification, mitigation and monitoring. There is no separate risk unit to efficiently carry out the risk management function as a result corporate risks are not identified, and no risk assessments are conducted. No risk management documents approved for 2025/26 There is no approved risk management policy risk management strategy, risk management implementation plan, Risk register was compiled but it is not regularly updated There is no approved business continuity plan in place. Municipality vulnerable and exposed to all risks | Approval of risk management documents for FY2025/26 (Risk management policy, Risk management plan, Risk Register, | In-house | In-house | NCR/CRO | 2027-01-01 | Annually | Risks mitigated | Council approved reports and sugned resolutions | Financial benefits to be realised through improved governance efficiencies and systems with checks and balances in place
|  |  | Quarterly progress reporting to Risk management committee on implementation of the risk management plan | In-house | In-house | NCR/CRO | 2027-01-01 | Quarterly | Risks mitigated | Approved reports and sugned resolutions | Financial benefits to be realised through improved governance efficiencies and systems with checks and balances in place
PILLAR TWO: INSTITUTIONAL AND ORGANISATIONAL DEVELOPMENT
1 | OPERATING MODEL | The review of the operating model has not been conducted. Over-reliance on contractors The municipality has two satellite offices and the central office. The municipality signed the MOU with NMMDM for the provision of water services | Utilize the strengths identified to establish a cost-efficient service delivery model | Internal | National Cogta | NCR/MM | 2027-01-01 | 2027-05-31 | approved costs efficient operating model | approved costs efficient operating model | Financial benefits to be realised through improved institutional efficiencies and systems with checks and balances in place
|  |  | Reduce the proportion of contracted services to the acquired internal resources | Internal | internal | NCR/MM | 2027-01-01 | 2027-01-31 | 60 % reduction on contracted services in Q1 2025/26FY | 61 % reduction on contracted services in Q1 2026/27FY | Financial benefits to be realised through improved institutional efficiencies and systems with checks and balances in place
|  |  | Optimise the capacity of satellite offices to deliver services and customer care. | Internal | internal | NCR/MM | 2027-01-01 | 2027-06-30 | 100% functional satellite offices with customer care facilities an functions | 100% functional satellite offices with customer care facilities an functions | Financial benefits to be realised through improved institutional efficiencies and systems with checks and balances in place
|  |  | Identify all employees associated with the services as a going concern | Internal | internal | NCR/MM | 2027-01-01 | 2027-03-31 | ringfence all 128 employees as a going concern, (employee follow functions principle apply) | ringfence all 128 employees as a going concern, (employee follow functions principle apply) | Financial benefits to be realised through improved institutional efficiencies and systems with checks and balances in place
2 | ORGANISATIONAL STRUCTURE | The municipal council approved the revised organizational structure during its May 2025 meeting. However, the structure is unfunded and bloated; The current structure was costed at R296 million with 724 employees, while the new proposed structure is projected to cost R300 million with 836 employees. The migration and placement policy has been agreed upon, and consultation with labour has been finalized for implementing the new structure. Job evaluation has not been conducted DLM still utilises the Van der Merwe system of Job evaluation. Job descriptions are not yet finalised; only the manager's job descriptions are completed. | Streamlined the organisational structure to be more efficient, considering the municipality's size and budget | Internal | internal | MM | 2027-01-01 | 2027-06-30 | conduct an organizational structure review based on the same size organization with lean and mean principles | conduct an organizational structure review based on the same size organization with lean and mean principles | Financial benefits to be realised through improved institutional efficiencies and systems with checks and balances in place
|  |  | Finalize all Job Evaluation processes in line with the Task system and request assistance from SALGA and Cogta. | Salga/ Cogta | Salga/Cogta | Direct: HR | 2027-01-01 | 2027-03-31 | completed job evaluation process with detailed financial implications | completed job evaluation process with detailed financial implications | Financial benefits to be realised through improved institutional efficiencies and systems with checks and balances in place
|  |  | Test the staff establishment for cost efficiency and affordability | internal | NCR | NCR / MM/ CFO | 2026-01-01 | 2027-02-28 | cost the current placements and all the vacancies in the organizational structure | detailed costing of the placements and vacancies | Financial benefits to be realised through improved institutional efficiencies and systems with checks and balances in place
|  |  | Develop enriched job descriptions for improved employee utilization | Salga/ Cogta | Salga/Cogta | Direct: HR | 2027-01-01 | 2027-04-30 | 60% reviewed job descriptions based on best practice | 60% reviewed job descriptions based on best practice | Financial benefits to be realised through improved institutional efficiencies and systems with checks and balances in place
3 | EMPLOYEE COST | Employee-related costs are the primary cost driver of operating expenditure, accounting for 50% of total OPEX, exceeding the norm of 25-40% as per Treasury Circular 71. Excessive overtime expenditure cannot be justified, as the municipality's controls are insufficient. 40 hours of overtime as per the BCEA, reduced to 20 hours as part of the cost containment strategy. The total incurred overtime expenses for the 2024/25 financial year are R24 619 792 million, and the June 2025 costs are R2 037 532. The actual employee costs remain at R338.6 million. The segregation of roles between Finance, Payroll, and HR Payroll needs to be clarified, as there are overlapping areas of concern. Annual salary increases approved for 2024/25 for all employees. Councillors also submitted upper limit salaries to the MEC, awaiting concurrence from Cogta. 3rd party payments are not up-to-date for 11 months to the value of R68 million Only medical aid paid up to 1 month in areas (September in areas) NO guarantees for salary payment for Nov and Dec 2025 due to insufficient budget, since all salaries are dependent on the equitable share Leave management controls are insufficient and pose a risk in the management of the leave system and employee leave balances. | Review the organisational structure to provide for payroll segregation | Internal | internal | Direct: HR | 2027-01-01 | 2027-06-30 | report on segregation of payroll roles between HR and Finance | report on segregation of payroll roles between HR and Finance | Financial benefits to be realised through improved institutional efficiencies and systems with checks and balances in place
|  |  | Reduce employee costs to 43% in line with budget | internal | NCR | NCR/MM | 2026-01-01 | 2027-06-30 | reduced employee costs to 45% of the operating costs in the 2Q in the 2025/26FY | reduced employee costs to 45% of the operating costs in the 2Q in the 2025/26FY | Employee Cost: <43 per cent of OPEX (10 per cent reduction) Councillor REM: 100 per cent per Gazetted maximums, subject to FRP Progress
|  |  | Reduce the areas on 3rd-party payments arrears | Internal | internal | NCR/MM/CFO | 2027-01-01 | 2027-03-31 | 3rd party payments reduced by R25 Million in the first quarter of 2026/27FY | 3th party payments reduced by R25 Million in the first quarter of 2026/27FY | R25 million
|  |  | Minimise areas on medical aids for the well-being of employees | Internal | internal | NCR/MM/CFO | 2027-01-01 | 2027-03-31 | 100% up to date payment on areas for medical aid on the 4th Quarter of 24/25 FY | 100% up to date payment on areas for medical aid on the 4th Quarter of 24/25 FY | Financial benefits to be realised through improved institutional efficiencies and systems with checks and balances in place
|  |  | Communicate future challenges regarding the timely payment of salaries to employees. | Internal | internal | NCR/MM | 2027-01-01 | Monthly | number of memos issued on non payment of salaries and general communication to employees | number of memos issued on non payment of salaries and general communication to employees | Financial benefits to be realised through improved institutional efficiencies and systems with checks and balances in place
|  |  | Conduct a leave audit for all employees and develop an electronic leave record for each employee. | Internal | internal | Direct: HR | 2027-01-01 | 2027-04-30 | leave audit report and Sage system optimisation | leave audit report and Sage system optimisation | Financial benefits to be realised through improved institutional efficiencies and systems with checks and balances in place
4 | FILLING OF CRITICAL VACANCIES | All senior management positions remain vacant. Parallel Appointment of officials in similar positions. Irregular employment practices. Lack of vacancy prioritization in line with the affordability ratio of the municipality. The council approved the appointment of 70 additional temporary workers in July 2025; however, they were terminated due to financial constraints. Family-related appointments. Irregular appointment in acting positions and exceeded the regulated acting period of 3 months. High Vacancy Rate in Management Levels at 90%. There is a high vacancy rate in all technical services areas. (Electricity, Water, Sanitation, and Roads) | Enforce the recruitment policy and consequence management for irregular appointments. | Internal | internal | MM | 2027-01-01 | 2027-03-31 | terminate and ensure consequence management on all irregular appointment | terminate and ensure consequence management on all irregular appointment | Financial benefits to be realised through improved institutional efficiencies and systems with checks and balances in place
|  |  | Minimise all direct family-related appointments in similar departments and reporting to each other | internal | internal | MM/ALL HODS | 2027-01-01 | 2027-02-28 | cautionary appointments be made to avoid conflict of interest | cautionary appointments be made to avoid conflict of interest | Financial benefits to be realised through improved institutional efficiencies and systems with checks and balances in place
|  |  | Prioritise for filling management posts | Internal | internal | NCR/MM | 2027-01-01 | 2027-03-31 | advertised senior management positions | number of post field for management roles | Financial benefits to be realised through improved institutional efficiencies and systems with checks and balances in place
5 | STAFF VERIFICATION AND QUALIFICATION AUDIT | The employee verification exercise was conducted but not completed. To date, 40 employees have not been verified. The payroll audit was not conclusive and remains outstanding. | Conduct annual employee verification | internal | CoGTA/SALGA | NCR/MM | 2027-01-01 | 2027-06-30 | report on staff verification | report on staff verification | Reduced REM Cost in line with Financial Target
6 | STAFF DISCIPLINE | Code of conduct not enforced. Three employees were charged with fraud for transacting in the municipal account without the authorization of the municipal manager. The employees were found guilty. Ten employees were charged with misconduct, malicious damage to property, and violent behaviour. The suspensions of senior management members, including the Chief Financial Officer, the Director of Corporate Services, and the acting Municipal Manager and PMU Manager, resulted in instability and a lack of accountability. Manager for water services on prolonged sick leave The ethical behaviour of employees and the code of conduct were not efficiently managed. Dereliction of duty by Managers and employees. Sporadic incidents of crime were also reported in DLM (e.g., holding people hostage, riots, kidnappings, etc.) No municipality can function in a chaotic and unsafe environment. | Enforce code of conduct | Internal | internal | Direct: HR | 2027-01-01 | Monthly | expedite all disciplinary cases for resolution and test prospects of success on all matters | expedite all disciplinary cases for resolution and test prospects of success on all matters | Financial benefits to be realised through improved institutional efficiencies and systems with checks and balances in place
|  |  | Provide training on ethical standards and value-based change management intervention to all employees | Internal | internal | Direct: HR | 2027-01-01 | 2027-03-31 | training report on ethical standards and change management | training report on ethical standards and change management | Financial benefits to be realised through improved institutional efficiencies and systems with checks and balances in place
|  |  | Conduct an employee utilization survey and manage employee performance | Internal | cogta/salga | NCR/MM | 2027-01-01 | 2027-04-30 | report on staff utilization and approach on how to deal with redundant staff | report on staff utilization and approach on how to deal with redundant staff | Financial benefits to be realised through improved institutional efficiencies and systems with checks and balances in place
|  |  | Identify elements of criminality and enforce the code of conduct | Internal | internal | NCR | 2027-01-01 | 2027-03-31 | number of criminal cases resolved against delinquent employees | number of criminal cases resolved against delinquent employees | Financial benefits to be realised through improved institutional efficiencies and systems with checks and balances in place
7 | CONSEQUENCE MANAGEMENT | There is a general disregard for compliance with key legislation, with no consequences for transgressions. No updated consequence management policies. | Review and update consequence management | Internal | internal | MM | 2027-01-01 | 2027-03-31 | approved consequence management policy | approved consequence management policy | Financial benefits to be realised through improved institutional efficiencies and systems with checks and balances in place
|  |  | Cascade PMS to all employees | internal | Internal | Director: HR | 2027-01-01 | 2027-02-28 | number of employees with performance contracts | signed performance agreements | Financial benefits to be realised through improved institutional efficiencies and systems with checks and balances in place
8 | PERFORMANCE MANAGEMENT | The municipality lacks approved internal policies and procedures to manage the collection, recording, processing, monitoring, and reporting of performance information. The majority of the indicators are not well-defined, and inconsistencies between the SDBIP and APP limit the testing of the reliability of the performance indicators and their related targets. The lack of effective records management has been the primary cause of the repeated disclaimers of opinions on performance information issued by the AGSA over the past three consecutive financial years. PMS is not cascaded to staff below S56/57 managers. | Training all managers on the management of performance | Internal | internal | Direct: HR | 2027-01-01 | 2027-04-30 | attendance registers on the training of managing performance | attendance registers on the training of managing performance | Financial benefits to be realised through improved institutional efficiencies and systems with checks and balances in place
|  |  | Review all indicators to be consistent with the IDP and the APP | Internal | internal | Cogta/Salga | 2027-01-01 | 2027-06-30 | reviewed performance indicators aligned with IDP and APP | reviewed performance indicators aligned with IDP and APP | Financial benefits to be realised through improved institutional efficiencies and systems with checks and balances in place
|  |  | Develop SOP for recording performance information and align it through the information management system | Internal | internal | NCR/MM | 2027-01-01 | 2027-06-30 | SOP report on recording performance information for audit purposes | SOP report on recording performance information for audit purposes | Financial benefits to be realised through improved institutional efficiencies and systems with checks and balances in place
9 | HR STRATEGY | The Municipality does not have an approved HR Strategy to support its operations. | Develop an HR strategy that can respond to key issues identified in the FRP and the IDP | Internal | internal | Direct: HR | 2027-01-01 | 2027-02-28 | Approved HR strategy | Approved HR strategy | Financial benefits to be realised through improved institutional efficiencies and systems with checks and balances in place
10 | KEY HR POLICIES | The municipality fails to properly implement approved Policies. The municipality is in contravention of the Occupational Health and Safety Act, as most of its buildings are not conducive to a productive organisation. The Department of Labour has already issued a contravention notice to the site offices of the municipality | Repair and maintain all buildings in line with the OHSA building standards | Internal | internal | MM | 2027-01-01 | Monthly | All buildings comply with OHSA standards | All buildings comply with OHSA standards | Financial benefits to be realised through improved institutional efficiencies and systems with checks and balances in place
|  |  | Appoint health and safety officials to build internal capacity and manage OHSA activities | Internal | internal | MM | 2027-01-01 | 2027-05-31 | list of all appointed officials task with OHSA responsibilities | list of all appointed officials task with OHSA responsibilities | Financial benefits to be realised through improved institutional efficiencies and systems with checks and balances in place
11 | SKILLS AND COMPETENCIES | The municipality lacks skilled employees in critical operational functions within service delivery and corporate support. Lack of critical skills in Finance departments (procurement, AFS, Revenue management, and Expenditure management. Lack of Skills in all Technical services (Electricity, Water, Waste management, and Roads). No employee development plans. Cogta conducted a qualification and skills audit; however, it did not include all employees. The Skills Development plan has been approved and submitted to the SETA | Training all employees in Finance on the minimum required competencies. | Internal | internal | Direct: HR | 2027-01-01 | 2027-07-01 | number of officials enrolled on competency based training for finance | number of officials enrolled on competency based training for finance | Financial benefits to be realised through improved institutional efficiencies and systems with checks and balances in place
12 | CHANGE MANAGEMENT | The municipality lacks internal capacity to manage change. The psychological effect of non-payment of salaries has affected employee morale and trust. The 3rd-party payment areas have created an unfavourable environment for employee relations. Unethical behaviour observed through employee grievances Politicised administration. Employee personal differences compromise professional relationships. The culture in DLM is not conducive to creating an effective and efficient municipality. Impunity, disregard for legislation, rules, processes, etc, have been raised as concerns | Establish an open communication with all employees on the challenges experienced by the municipality in the payment of salaries | internal | Cogta/National Treasury | NCR/MM | 2027-01-01 | 2027-03-31 | conduct employee satisfaction survey | report on management survey | Financial benefits to be realised through improved institutional efficiencies and systems with checks and balances in place
|  |  | Cultivate a culture that determines the values and cultural ethos for the municipality and enforces them. | Internal | internal | Direct: HR | 2027-01-01 | 2027-03-31 | present change management interventions | present change management interventions | Financial benefits to be realised through improved institutional efficiencies and systems with checks and balances in place
|  |  | Conduct team-building sessions to ensure employee cohesion | Internal | internal | Direct: HR | 2027-01-01 | 2027-02-28 | conduct team building sessions for employee cohesion | conduct team building sessions for employee cohesion | Financial benefits to be realised through improved institutional efficiencies and systems with checks and balances in place
|  |  | Depoliticize the administration | internal | Internal | NCR/MM | 2026-01-01 | 2027-03-31 | professionalise the employee group though ethics and behavioural change | professionalise the employee group though ethics and behavioural change | Financial benefits to be realised through improved institutional efficiencies and systems with checks and balances in place
|  |  | Enforce and reward the new culture to ensure sustainability | Internal | internal | Direct: HR | 2027-01-01 | 2027-03-31 | introduce performance award ceremonies for all employees | introduce performance award ceremonies for all employees | Financial benefits to be realised through improved institutional efficiencies and systems with checks and balances in place
|  |  | Establish the SOP for record management | internal | Internal | Manager records management | 2027-01-01 | 2027-02-28 | approved SOP for records management | approved SOP for records management | Financial benefits to be realised through improved institutional efficiencies and systems with checks and balances in place
13 | RECORDS MANAGEMENT | The municipality lacks a proper system to ensure the safekeeping of documentation that supports its financial statements and annual performance report. There is no record management policy, system, or procedure. Document management is lacking across all departments. Employees' records and system exist, but are not updated. The employee leave records management system is dysfunctional (manual forms are transferred into the system). The leave management policy is not being adhered to in some departments. Leave audit not done. The SAGE Electronic System is operational, but not optimised by the municipality. | Conduct a comprehensive leave audit | Internal | internal | Direct: HR | 2027-01-01 | 2027-02-28 | Report on comprehensive leave audit | report on comprehensive audit | Financial benefits to be realised through improved institutional efficiencies and systems with checks and balances in place
PILLAR THREE: FINANCIAL MANAGEMENT
1 | BUDGET MANAGEMENT | The municipality approved unfunded budgets for 5 consecutive years. The municipality’s 2025/26 MTREF Budget is unfunded with R2,1bn, after all the municipality’s liabilities are considered. Budget-related policies reviewed annually but not assessed for financial viability (increased revenue and reduced expenditure). There is a risk that the December 2025 equitable share grant funding of the municipality might be withheld (MIF funds used to pay salaries Manipulation of the budget estimates, revenue over estimated and expenditure under estimated to budget for operating surpluses, but realise deficits (Budget not credible and realistic). | Prepare a credible 2026/27 Adjustment Budget aligned with the set FRP financial targets. | In house | In house | CFO | 2027-01-01 | 2027-02-18 | Credible 2026/27 Adjustment Budget | Approved 2026/27 Adjustment Budget Council resolution | Repair and Maintennace: 3 per cent of OPEX (2026/27), and 4 per cent of OPEX (2027/28) Compliance to NT Budget Circular Alignment with FRP targets
|  |  | Review all budget related policies and assess for financial viability (increased revenue and reduced expenditure). | In house | In house | CFO | 2027-01-01 | 2027-04-30 | Budget related policies review for financial viability Demonstrated financial impact | Revised Budget related policies Council resolution
|  |  | Prepare a 2026/27 Budget Funding Plan aligned with the FRP strategies. | In house | In house | CFO | 2026-08-01 | 2026-08-31 | 2026/27 BFP 100% aligned with FRP | Approved 2026/27 BFP
|  |  | Prepare a credible 2027/28 MTREF Budget aligned with the set FRP financial targets. | In house | In house | CFO | 2027-01-01 | 2027-05-31 | Credible 2027/28 MTREF Budget | Final 2027/28 MTREF Budget
|  |  | The conditions set out for the Municipal Debt Relief as per MFMA Circular No. 124 should be considered carefully and implementation monitored by Council. | In house | In house | CFO | 2027-01-01 | Monthly | Eskom Debt Relief Compliance Plan 100% implemented | Eskom Debt Relief Compliance Plan and Progress
2 | BUDGET AND TREASURY OFFICE (BTO) | The BTO is lacking appropriate skills: Lacking appropriate skills, for example to prepare AFS. SCM = 4 positions filled. Revenue Management = 17 positions filled + 1 contract worker. Budget Management = 3 positions filled + 1 contract worker. Expenditure = 3 positions filled. Asset Management – no employees. | Filling of critical vacancies in the BTO, subject to affordability and based on anticipated improvement in liquidity. | In house | In house | CFO | 2027-01-01 | 2027-06-30 | Improved BTO skills and capacity | Letters of appointment | Increased revenue and reduced expeniture to be realised through improved financial management efficiencies and systems with checks and balances in place
3 | REVENUE MANAGEMENT (METERED SERVICES AND VENDING) | No Revenue Enhancement Strategy in place. The Equitable Share for Free Basic Services is allocated to the NMMDM (average R13m per month) and not shared with DLM. Municipality does not possess employees with the skills set necessary to perform the function. The meter reading function has been outsourced for an extended period, therefore the require skills have not been maintained in-house. No reconciliations performed for prepaid vendors. Water Meters • Total of 18 101 meters in the systems of which only 448 (2,5 per cent) are read and billed with a total of 17 653 not read and billed. • Lack of water meters for replacements and new connections. • Vandalism of older existing meters for brass content. • Illegal connections and/or unmetered losses. Electricity Meters • Electricity meters are 1261 in total, 273 read and billed with a total of 988 unaccounted for. • Lack of meters for replacement and new connections. • Abridgement of electricity meters (legal and illegal). • Only around 10% of residential properties have meters. No meter audits performed for either Water or Electricity meters over at least the past 10 years. Challenge of prepaid meters which are not purchasing The municipality applied for the National Treasury smart meter grant and it was not granted due to failure to achieve the debt relief conditions, but the grant was actually going to assist the municipality to achieve as it was going to assist with revenue enhancement. Lack of control over the electricity services: Electricity revenue related services are performed by a service provider, Cigicel including monthly billing, and ultimately the recovery of electricity charges. The Service provider handles all electricity-related issues, and the municipality has limited control and oversight over the process. Broken/Faulty meters. Limitations of the Financial System: The municipality has moved to a new service provider and are encountering significant limitations with regards to the billing of consumers, over and above the limited meter information (No billing in 2022/23). | Develop and implement a Revenue Enhancement Strategy. | In house | In house | NCR, CFO | 2027-01-01 | 2027-02-01 | Improved revenue in line with FRP targets | Approved RES RES Progress Reports | 2025/26 + Growth (0,5 per cent) (in accordance with consumer demand and revised tariff structure and levels) + NERSA Forecast (8.76 per cent) CPIX: 4,2 per cent 5% additional increase in trading revenue due to improved billing 3% increase from: • Improved metering/ Reduced losses • Improved data integrity and billing • Improvement in controls leading to decreased illegal connections • Phasing in of cost-reflective tariffs.
|  |  | Revise the contract on electricity revenue related services performed by Cigicel to strengthen the municipality’s control and oversight over the process. | In house | In house | NCR, CFO | 2027-01-01 | 2027-02-28 | Increased electricity revenue in line in FRP targets | Revised CIGICEL Contract
|  |  | Training on use of financial systems and procedures for uploading municipal information, including valuation rolls, tariff lists etc. | In house | In house | CFO | 2027-01-01 | 2027-03-31 | FMS improved efficiencies | Training schedule
|  |  | Outstanding consumer debtors that are increasing should be monitored by stringent credit and debt collection policy implementation for the ensuing months. | In house | In house | CFO | 2027-01-01 | Monthly/ Ongoing | Reduced debtors | Cut-off lists
|  |  | Meter reading must be done monthly and reconciled with the financial system. | In house | In house | CFO | 2027-01-01 | Monthly | 100% Complete and accurate billing | Meter reading progress reports
|  |  | Review the Debtor’s Book regularly for write-offs. | In house | In house | CFO | 2027-01-01 | Quarterly | Reduced debtors | Write-Off Reports Council resolutions
|  |  | Implement targeted strategies to address this segment and explore options such as outreach programs, financial counselling, and instalment plans to assist residents in managing their debt. | In house | In house | CFO | 2027-01-01 | 2027-06-30 | Improved collection rate | Progress Reports
4 | REVENUE MANAGEMENT (PROPERTY RATES) | Valuation roll and the billing system contains errors: No VR reconciliation No property rates policy or by-law in place | Prepare the VR reconciliation and correct all variances | In house | NT Tariff Assessment Tool | CFO | 2027-01-01 | Monthly | Increased property rates revenue in line with FRP targets | VR Recons | 2025/26 Budget + CPIX (4,2 per cent) +growth (0,5 per cent) Collection Rate: 93 per cent 2025/26 Budget + CPIX (4,2 per cent) +growth (0,5 per cent) R102,8 million (2026/27) R107,4 million (2027/28) Collection Rate: 93 per cent
|  |  | Approval of property rates policy and publish by-laws | In house | In house | CFO | 2027-01-01 | 2027-05-31 | Improved legislative complaince | Property Rates Policy By-Laws Council resolutions
5 | REVENUE MANAGEMENT (COLLECTION) | Low revenue collection rates (44 per cent in 2024/25). Poor data integrity on the billing system. Lack of integration of the revenue value chain with town planning. Following a Court Order on 25 Oct’17, 8 big electricity pay directly to Eskom. Billing and financial system errors. | Cleansing of billing data | In house | S154 support PT | CFO | 2027-01-01 | 2027-04-30 | Improved data integrity and billing | Data Cleansing Report | Collection Rate 70% (2026/27), and 80% (2027/28)
6 | DEBTORS MANAGEMENT | Net debtors’ days increased from 992 days in 2019/20 to 1060 days in 2024/25. Debtors book could be overstated, and not reviewed regularly to determine how much can realistically be collected. Municipality has weak controls in debtor’s management. Some of the major debtors are councillors, staff and government institutions which do not pay their utilities on time. No credit control policies in place to guide provision of services to non-paying customers. Resistance to implement credit control measures. Net debtors’ days increased from 992 days in 2019/20 to 1060 days in 2024/25. | Consultation with financial system service provider as to the root cause/s for billing inconsistencies. | In house | In house | NCR, CFO | 2027-01-01 | 2027-03-31 | Improved billing | IT Steercom Progress Reports | Debt Impairment: 100 per cent of billed revenue minus realistic Collection Rate
7 | COST-REFLECTIVE TARIFFS | All trading services function with operating deficits. Non-cost reflective tariffs. The municipality does not have an approved tariffs policy or structure in place. | Implementation of cost-reflective tariffs in a phased approach to be an integral part of performance agreement of the CFO. | In house | In house PT Advise | CFO | 2027-01-01 | 2027-06-30 | Increased Trading Revenue Operating surplusses | Tariff Policy and structure CFO Perfromance Agreement | Increased revenue and reduced expeniture to be realised through improved financial management efficiencies and systems with checks and balances in place
|  |  | Verify tariff increases for cost-reflectiveness. | In house | In house | CFO | 2027-01-01 | Annually | Increased Trading Revenue Operating surplusses | Tariff Policy and structure CFO Perfromance Agreement | Increased revenue and reduced expeniture to be realised through improved financial management efficiencies and systems with checks and balances in place
8 | SUPPLY CHAIN MANAGEMENT | The SCM unit is fairly functional and currently consists of 4 officials, however, there is a concern with regards to the competence levels of the staff members. SCM Committees not properly functional. No procurement plan could be submitted. Outdated SCM related policies. Oversight of the SCM function by accounting officer and Council is not consistent due to instabilities in these posts. SCM procedures are not documented. | Focus on Demand Management, long-term planning and the linkage to Procurement plans (in return it can greatly stimulate and enable economic growth through strategic alignment). | In house | MFIP SCM Advisor | CFO | 2027-01-01 | 2027-04-30 | Improved value-for-money procurement | Demand Management Strategy | Increased revenue and reduced expeniture to be realised through improved financial management efficiencies and systems with checks and balances in place
|  |  | Implement SCM SOPs compliant with legislation and reforms | In house | MFIP SCM Advisor | CFO | 2027-01-01 | 2027-05-31 | Improved SCM process and compliance efficiencies | Approved SCM SOPs | Increased revenue and reduced expeniture to be realised through improved financial management efficiencies and systems with checks and balances in place
|  |  | Develop a SCM Compliance Matrix for monitoring compliance | In house | MFIP SCM Advisor | CFO | 2027-01-01 | 2027-03-31 | Improved SCM compliance No new UIFW | Approved SCM Compliance Matrix | Increased revenue and reduced expeniture to be realised through improved financial management efficiencies and systems with checks and balances in place
|  |  | Clearly define the system of SCM delegations and sub- delegations as required by SCM Regulation 4 and 5. | In house | In house | CFO | 2027-01-01 | 2027-04-30 | Improved SCM operational efficiencies | Approved SCM delegations | Increased revenue and reduced expeniture to be realised through improved financial management efficiencies and systems with checks and balances in place
|  |  | Prioritise the training of officials to ensure compliance to the municipal minimum competency requirement for SCM officials, request PT to provide the training | In house | In house | CFO | 2027-01-01 | 2027-05-31 | Improved SCM operational efficencies | SCM Training Schedule | Increased revenue and reduced expeniture to be realised through improved financial management efficiencies and systems with checks and balances in place
|  |  | Implement a skills development plan for SCM officials as required by SCM Regulation 8 (LG SETA Application) | In house | In house | CFO | 2027-01-01 | 2027-03-31 | Improved SCM skills and capacity | SCM Skills Development Plan and Progress Reports | Increased revenue and reduced expeniture to be realised through improved financial management efficiencies and systems with checks and balances in place
9 | COST CONTAINMENT AND CASH FLOW MANAGEMENT | No compliant Cost Containment Policy. Cash flow management committee not in place. Weak controls over cash and bank. No financial discipline. Irregular appointment of security service provider and inflated and unnecessary cost. | Implement the Cost Containment Policy and report progress against set saving targets/ Phased-in implementation of cost cutting measures on allowances and entertainment expenses. | In house | In house | NCR, CFO, All Senior Managers | 2027-01-01 | Monthly | Reduced cost in line with FRP targets | Monthly Cost Containment Progress Reports | Targeted ratios: • Cash Coverage: 0,5 Months • Current Ratio: 1.0:1 Maintain savings from 2025/26 BFP and ensure full compliance with regulations + further savings
|  |  | Sustain the cash flow management committee to ensure cost-containment measure are implemented and monitored effectively. | In house | In house | NCR, CFO | 2027-01-01 | Weekly/ Monthly | Cost contained in line with FRP targets | CFM Committee Minutes
10 | FINANCIAL CONTROL ENVIRONMENT | Consultants are contracted for critical finance functions without proper performance monitoring. Financial system challenges have affected billing and reporting since 2020. Staffing constraints in critical finance roles. Poor internal financial controls. | Assess IT controls on the financial system to prevent unauthorised transactions. | In house | In house | CFO, IT Manager | 2027-01-01 | 2027-02-28 | 100% effective IT controls on the FMS | Documented IT controls | Increased revenue and reduced expeniture to be realised through improved financial management efficiencies and systems with checks and balances in place
|  |  | Develop and implement SOPs for all financial functions. | In house | In house | CFO | 2027-01-01 | 2027-04-30 | Imroved effectiveness of financial management processes, systems and procedures | Approved SOPs | Increased revenue and reduced expeniture to be realised through improved financial management efficiencies and systems with checks and balances in place
11 | mSCOA | Non-adherence to MSCOA legislation. Key Functional mSCOA Modules not implemented. Lacking funding to develop the IT environment. No functional Steering committee for MSCOA implementation. No mSCOA Champion. No mSCOA Road Map developed. Data Strings not credible. | Ensure the MTREF Budget and supporting tables fully completed to ensure credibility. | In house | In house | CFO | 2027-01-01 | 2027-04-30 | 100% compliant MTREF Budget | mSCOA Compliant MTREF Budget | Increased revenue and reduced expeniture to be realised through improved financial management efficiencies and systems with checks and balances in place
|  |  | Promote the use of the FAQ database for all queries and report updates via forums (i.e., MAF, AWC). | In house | In house | CFO | 2027-01-01 | Monthly/ Ongoing | Improved mSCOA compliance | FAQ User Reports | Increased revenue and reduced expeniture to be realised through improved financial management efficiencies and systems with checks and balances in place
|  |  | Facilitate periodic in-house and external training on the use and implementation of the mSCOA charts | In house | In house | CFO | 2027-01-01 | Quarterly | Improved mSCOA skills | mSCOA Training Schedules | Increased revenue and reduced expeniture to be realised through improved financial management efficiencies and systems with checks and balances in place
|  |  | Sustain functional mSCOA Steering Committee. Perform on-site inspection and assessment of municipalities’ systems and implementation to determine compliance (circulars, legislation, regulation), vulnerability and progress of mSCOA implementation. | In house | In house | CFO, IT Manager | 2027-01-01 | Monthly | Functional mSCOA Steercom | mSCOA Steercom meeting minutes | Increased revenue and reduced expeniture to be realised through improved financial management efficiencies and systems with checks and balances in place
|  |  | Implement mSCOA Road Map | In house | In house | CFO, IT Manager | 2027-01-01 | Ongoing | Improved mSCOA implementation and compliance | mSCOA Progress Reports | Increased revenue and reduced expeniture to be realised through improved financial management efficiencies and systems with checks and balances in place
12 | FINANCIAL REPORTING | Lack of capacity and competence to carry out the financial reporting function. Inaccurate financial reporting The financial reporting function has been grossly mishandled by consultants as evidenced by the consecutive disclaimer of opinions from AGSA. The underlying financial records for financial reporting affected by IT systems challenges. Non-adherence to AGSA and NT submission timeframes. | PT to monitor in-year reporting and MFMA compliance | In house | PT Oversight | CFO | 2027-01-01 | Monthly | Credible financial reports 100% MFMA Compliance | In-year Financial Reports | Increased revenue and reduced expeniture to be realised through improved financial management efficiencies and systems with checks and balances in place
|  |  | SALGA to assist with AFS preparation, including capacity building. | In house | SALGA | CFO | 2027-01-01 | 2027-05-31 | Improved internal skills for AFS preparation | Training Scope and Schedule Attendance Record | Increased revenue and reduced expeniture to be realised through improved financial management efficiencies and systems with checks and balances in place
|  |  | Keep an Audit File in preparation for the annual external audit (compliant with the NT and AG norms and standards). | In house | In house | CFO | 2027-01-01 | Monthly for end June readiness | 100 % readiness for external audit (AG) | Audit File Index and Records | Increased revenue and reduced expeniture to be realised through improved financial management efficiencies and systems with checks and balances in place
13 | EXPENDITURE MANAGEMENT | Creditors days increased from 2087 days in 2022/23 to 3188 days in 2024/25 which means the Municipality is taking a very long time to settle amounts owed. No grant management policy in place. Approved for Eskom Debt Relief, but not complying (Risk that Eskom may take over). Non-payment of services within 30 days of receipt of the invoice as required by the MFMA. Poor relationship between municipality and suppliers/ creditors due to non-payment. Irregular payments made from the bank accounts | Training to be provided to officials on creditors reconciliations, to prevent overpayment of invoices or interest/penalties levied on late payment | In house | In house | CFO | 2027-01-01 | 2027-03-31 | Improved Expenditure Management capacity | Training schedules and attendance registers | 5% reduction in water/ electricity losses through improved metering and decreasing illegal connections. Contracted Services – Norm 2-5 per cent of OPEX: <5,5 per cent Other expenditure: CPI increase (3 per cent) + Growth (0,5 per cent) – 4 per cent reduction from cost containment measures Contracted Services maximum: R23,8 (2026/27), and R23,6 (2027/28)
|  |  | Prepare creditors reconciliations for all creditors | In house | In house | CFO | 2027-01-01 | Monthly | 100% Creditors reconciliation done monthly | Creditor reconciliations
|  |  | Implement rigorous financial controls and closely adhere to the budget to manage and mitigate overspending, particularly in employee-related costs and councillor remunerations. | In house | In house | NCR, MM, CFO | 2027-01-01 | Ongoing | No irregular or unauthorised expenditure | Documented expenditure controls
|  |  | Recognise expenditure when incurred and capture immediately on the system/ use GR's and/ or creditors sub-system | In house | In house | CFO | 2027-01-01 | Daily | Improved accuracy of transacting | Financial Report by CFO
|  |  | Consequence Management for misappropriation of funds. | In house | In house | NCR, MM, Corporate Director | 2027-01-01 | Daily/ Monthly | Consequence Management for all misaapropriations of funds | DB Reports
14 | ASSET MANAGEMENT | No standalone asset management unit that ensures assets are maintained and safeguarded. Sound asset management practices like physical verifications not implemented as there is no standalone asset management unit. Asset management relating to capital projects does not align with the critical needs of the municipality. No up-to-date Asset Management Policy FAR not annually updated. | Train assigned staff on best practices for efficient and effective asset management | In house | MFIP AM Advisor | CFO, Asset Manager | 2027-01-01 | 2027-04-30 | Improved AM Skills | AM Training Schedule and attendance records | Increased revenue and reduced expeniture to be realised through improved financial management efficiencies and systems with checks and balances in place
|  |  | Implement approved Asset Management Policy. | In house | In house | CFO, BTO, Asset Manager | 2027-01-01 | 2027-06-30 | Improved AM operational efficiencies | AM Policy and Implementation Progress Reports | Increased revenue and reduced expeniture to be realised through improved financial management efficiencies and systems with checks and balances in place
|  |  | Implement documented Standard Operating Procedures, Segregation of duties and cross-functional roles and duties outlined. | In house | In house | CFO, BTO, Asset Manager | 2027-01-01 | 2027-04-30 | Improved AM operational efficiencies | Approved SOPs and Implementation Reports | Increased revenue and reduced expeniture to be realised through improved financial management efficiencies and systems with checks and balances in place
|  |  | Increase the budgeted ratio for repairs and maintenance as a percentage of PPE. | In house | In house | CFO, Technical Director | 2027-01-01 | 2027-12-31 | Increased R&M Budget allocations | Approved MTREF Budget | Increased revenue and reduced expeniture to be realised through improved financial management efficiencies and systems with checks and balances in place
15 | INDIGENT MANAGEMENT | Poor indigent household registration. Outdated Indigent Policy. No verification of indigent debtors. No appropriate write-offs of Indigents Debt. FBS allocations could not be confirmed. | Implement vetting procedures prior to approval of indigents. | In house | In house | CFO | 2027-01-01 | 2027/066/30 | Policy compliant indigent registration | Vetting Report | Increased revenue and reduced expeniture to be realised through improved financial management efficiencies and systems with checks and balances in place
|  |  | Involve Ward Committees in indigent registration. | In house | NCR, MM | NCR, MM, Speaker | 2027-01-01 | 2027-06-30 | Functional Ward Committees | Ward Committee communications | Increased revenue and reduced expeniture to be realised through improved financial management efficiencies and systems with checks and balances in place
|  |  | Capping of FBS for indigent households. | In house | In house | CFO, Technical Director | 2027-01-01 | 2027-03-31 | Improved accuracy on FBS allocation | FBS Capping Policy | Increased revenue and reduced expeniture to be realised through improved financial management efficiencies and systems with checks and balances in place
PILLAR FOUR: SERVICE DELIVERY AND INFRASTRUCTURE DEVELOPMENT
1 | MASTER PLANNING | Senior Management positions in the service delivery unit are vacant and this hampers effective service delivery. | Appoint qualified technical personnel (engineers, planners, and GIS specialists) to manage the infrastructure systems and support Master Plan development. | In-house | In-House | Technical Director, NCR | 2026-01-01 | 2026-12-30 | Appointment of the Technical Director | Letter of Appointment of Technical Director | Financial benefits accruing from improved service delivery efficiencies
|  | The National Spatial Development Framework requires that municipal SDF is reviewed at least every five years to remain aligned with national and provincial policies. SDF provides the policy framework that underpins the municipal Land Use Scheme (LUS) and its absence means the municipality is not able to plan accordingly and appropriately | Update Municipal Land Use Schemes. | MISA | MISA | MM, NCR Service Delivery Expert | 2026-01-01 | 2026-12-30 | Updated Land Use Scheme | Land Use Scheme Maps | Financial benefits accruing from improved service delivery efficiencies
2 | CAPITAL AND GRANT FUNDED PROJECTS | Underspending on capital projects due to attachment of bank account by SARS Contractors suspending work on sites due to non-payment | (1) Develop and implement a Senior Management Stability Framework to strengthen leadership continuity and capacity; (2) Develop and implement a Rollover Project Implementation Plan to ensure completion of 2021/2022 outstanding projects; (3) Secure approval for rollover budget adjustments and ensure funds are properly committed in the municipal financial system; (4) Improve the performance of the Project Management Unit (PMU) and enhance grant management, ensuring full compliance with relevant legislation. | CoGTA Support | In-House | Technical Director, NCR Technical Expert | 2027-01-01 | 2027-12-30 | Completion of training on Infrastructure Delivery Management; Project Register Project Progress (completion and expenditure) Timeous payment of service providers. 100% Grant expenditure according to conditions. | Proof of Training on Infrastructure Delivery Management Training Monthly Project Progress Register | Financial benefits accruing from improved service delivery efficiencies
|  | Payments Process for contractors is delayed due to validation process by CoGTA/MISA on how the service providers were appointed and confirmation of work done. The delay caused by this process result in the service leaving site | (1) MISA and COGTA to propose a process plan which should be incorporated in the implementation plan for the contractor appointment and timelines performance parameters during project execution; (2) Provide annual training sessions for PMU staff and management on project management best practices, grant regulations, and legislative requirements | CoGTA Support | In-House | Technical Director, NCR Technical Expert | 2027-01-01 | 2027-12-30 | Zero delays in payments. No contract termination due to late payment. | MISA/CoGTA Process Plan for project inspection and payments. | Financial benefits accruing from improved service delivery efficiencies
3 | BULK WATER SUPPLY AND RETICULATION | Inadequate water supply to meet demand due to low borehole yields (11,6Ml/day vs demand of 19Ml/day), water losses and electricity loadshedding affects Water Losses @ 58% | Form a technical team consisting of representatives from NMMDM, Ditsobotla Municipality, and MISA | NMMDM, MISA, DWS, ESKOM, DEDECT,SALGA | In-House | Technical Director, NCR Technical Expert | 2027-01-01 | 2027-12-30 | Technical Workstream Meeting Schedule Meeting minutes | Meeting Schedule Meeting Agenda Meeting minutes and resolutions | Financial benefits accruing from improved service delivery efficiencies
|  | There is water rationing due to inadequate water supplies shortage | Develop and implement a Water Conservation and Water Demand Management (WC/WDM) Plan. | NMMDM, MISA, DWS, ESKOM,SALGA | In-House | Technical Director, NCR Technical Expert | 2027-01-01 | 2027-12-30 | Water Losses reduction Ml/d production increase | Water loss calculation report Improvement in production yields | 5% water loss reduction. Generate additional R12m from installation/repair of additional 4000 water meters.
|  | The municipality is unable to account for water it purchases | Identify all priority sites and complete the installation and commissioning of bulk water meters 100% of targeted sites with monthly progress reports submitted to track completion and functionality. | NMMDM, MISA, DWS, ESKOM,SALGA | In-House | Technical Director, NCR Technical Expert | 2027-01-01 | 2027-12-30 | Water Losses reduction Ml/d production increase | Water loss calculation report Improvement in production yields | 5% water loss reduction. Generate additional R12m from installation/repair of additional 4000 water meters.
|  | Losses are not recorded; therefore, it is difficult to quantify them and identify cost-saving solutions. | Procure and install meters for at least 25% of unmetered consumers every quarter until 100% coverage is achieved. | NMMDM, MISA, DWS, ESKOM,SALGA | In-House | Technical Director, NCR Technical Expert | 2027-01-01 | 2027-12-30 | Water Losses reduction Ml/d production increase | Water loss calculation report Improvement in production yields | 5% water loss reduction. Generate additional R12m from installation/repair of additional 4000 water meters.
|  | The municipality is not quantifying water losses. | Conduct systematic leak detection and repair in high-loss zones. | NMMDM, MISA, DWS, ESKOM,SALGA | In-House | Technical Director, NCR Technical Expert | 2027-01-01 | 2027-12-30 | Water Losses reduction Ml/d production increase | Water loss calculation report Improvement in production yields | 5% water loss reduction. Generate additional R12m from installation/repair of additional 4000 water meters.
|  |  | Ensure all identified leaks are repaired within 14 days of detection | NMMDM, MISA, DWS, ESKOM,SALGA | In-House | Technical Director, NCR Technical Expert | 2027-01-01 | 2027-12-30 | Water Losses reduction Ml/d production increase | Water loss calculation report Improvement in production yields | 5% water loss reduction. Generate additional R12m from installation/repair of additional 4000 water meters.
|  |  | Track the number of leaks detected, repaired, and reduction in water losses monthly | NMMDM, MISA, DWS, ESKOM,SALGA | In-House | Technical Director, NCR Technical Expert | 2027-01-01 | 2027-12-30 | Water Losses reduction Ml/d production increase | Water loss calculation report Improvement in production yields | 5% water loss reduction. Generate additional R12m from installation/repair of additional 4000 water meters.
|  | Leakage of old asbestos pipeline Community protests incorrectly directed to the local instead of the District on powers and functions outside the competency of municipality | Develop a phased replacement program for asbestos pipelines using safe, modern materials (e.g., HDPE, PVC). | NMMDM, MISA, DWS, ESKOM,SALGA | In-House | Technical Director, NCR Technical Expert | 2027-01-01 | 2027-12-30 | km pipeline replaced | Route completed | Financial benefits accruing from improved service delivery efficiencies
|  | Magalies Water billing both the municipality and the District for water provided through boreholes | Ensure clarity of roles, eliminate double billing, and guarantee accurate metering and transparent invoicing for water services. | NMMDM, MISA, DWS, ESKOM,SALGA | In-House | Technical Director, NCR Technical Expert | 2027-01-01 | 2027-12-30 | Water Service Provider mapping clarifying areas of jurisdiction from the District as the Water Service Authority | Agreement clarifying the role differentiation for Magalies Water | Financial benefits accruing from improved service delivery efficiencies
|  |  | Ensure accurate water measurement and billing by replacing all dysfunctional water meters. | NMMDM, MISA, DWS, ESKOM,SALGA | In-House | Technical Director, NCR Technical Expert | 2027-01-01 | 2027-12-30 | Number of meters replaced. | Progress report on meter installation | Financial benefits accruing from improved service delivery efficiencies
|  | Maintenance on water infrastructure owned by municipality done by the Ditsobotla LM municipality whilst the functions was given back to the District through a Court Order | Develop and implement a Transitional Water Infrastructure Handover Plan. | NMMDM, MISA, DWS, ESKOM,SALGA | In-House | Technical Director, NCR Technical Expert | 2027-01-01 | 2027-12-30 | Handover Plan | Handover Plan | Financial benefits accruing from improved service delivery efficiencies
|  | Distribution losses cannot be determined because Magalies Water has denied Ditsobotla access to boreholes. | Establish formal intergovernmental engagement with Magalies Water to secure access to borehole sites for data verification and monitoring. Submit a formal request to Magalies Water via the relevant intergovernmental forum | NMMDM, MISA, DWS, ESKOM,SALGA | In-House | Technical Director, NCR Technical Expert | 2027-01-01 | 2027-12-30 | Water Service Provider mapping clarifying areas of jurisdiction from the District as the Water Service Authority | Agreement clarifying the role differentiation for Magalies Water | Financial benefits accruing from improved service delivery efficiencies
4 | BULK ELECTRICITY SUPPLY AND RETICULATION | Existing water and electricity infrastructure is criminally vandalized or sabotaged | Apply to NERSA for approval of tariffs by March 2026 | NMMDM, MISA, DWS, ESKOM,SALGA | In-House | Technical Director, NCR Technical Expert | 2027-01-01 | 2027-12-30 | Tariff increase as per cost of supply study | Approval for tariff increase | Financial benefits accruing from improved service delivery efficiencies
|  |  | Use 8% top slice of MIG allocation on O&M | NMMDM, MISA, DWS, ESKOM,SALGA | In-House | Technical Director, NCR Technical Expert | 2027-01-01 | 2027-12-30 | 8% allocation for O&M | Budget Approved | Financial benefits accruing from improved service delivery efficiencies
|  |  | Develop municipal Demand Side Management Plan. | NMMDM, MISA, DWS, ESKOM,SALGA | In-House | Technical Director, NCR Technical Expert | 2027-01-01 | 2027-12-30 | Losses must we within the norm of 7-10% | DSM Plan on achieving 10% or less losses | Financial benefits accruing from improved service delivery efficiencies
|  |  | Conduct meter & customer audits. | NMMDM, MISA, DWS, ESKOM,SALGA | In-House | Technical Director, NCR Technical Expert | 2027-01-01 | 2027-12-30 | number of meters and condition | Meter audit report | Financial benefits accruing from improved service delivery efficiencies
|  |  | Install or repair geyser (hot water load management) control system | NMMDM, MISA, DWS, ESKOM,SALGA | OEM | Technical Director, NCR Technical Expert | 2027-01-01 | 2027-12-30 | Number of geysers controlled vs installed based | Gyser control project progress report | Financial benefits accruing from improved service delivery efficiencies
|  |  | Working with Security Management, devise and implement strategies to reduce vandalism and theft of infrastructure | NMMDM, MISA, DWS, ESKOM,SALGA | In-House | Technical Director, NCR Technical Expert | 2027-01-01 | 2027-12-30 | No. of theft incidents No. of vandalism incidents | Security Management Strategy and implementation plan for critical assets (substations. Boreholes, pumpstations) | Financial benefits accruing from improved service delivery efficiencies
5 | WASTE AND REFUSE REMOVAL | Landfill sites are not properly secured and safeguarded. There is unrestricted access by the public to the sites and to high-value equipmentThree landfill sites (Itsoseng, Tlhabologang, and Biesiesvlei) are non-functional and have been issued waste management licenses for closure and rehabilitation. | Install perimeter fencing and controlled entry gates around all landfill sites to prevent unauthorized access, scavenging, and illegal dumping. | In-House | In-House | Technical Director, NCR Technical Expert | 2027-01-01 | 2027-12-30 | Length of fence required to secure land fill sites vs fence installed | Fencing of landfill sites audit | Financial benefits accruing from improved service delivery efficiencies
|  |  | Develop and implement a compliance plan to meet all license requirements including conducting a gap analysis of current operations against license conditions, implementing corrective actions, and submitting a complete licensee application to the relevant regulatory authority | DEDECT | In-House | Technical Director, NCR Technical Expert | 2027-01-01 | 2027-12-30 | Gap Analysis indicators for landfill sites, remaining useful life, submission on system, audits, signage, security, licensing and conditions. | Gap Analysis Report | Financial benefits accruing from improved service delivery efficiencies
|  | Coligny and Lichtenburg landfill have not been maintained properly and both are not compliant with regulations for landfill sites. | Implement asset management principles by engaging qualified environmental and civil engineering experts to assess and determine the remaining useful life of all municipal landfill sites. | CFO | In-House | Technical Director, NCR Technical Expert | 2027-01-01 | 2027-12-30 | Airspace | Airspace Assessment Report | Financial benefits accruing from improved service delivery efficiencies
|  | Failure to finalise, approve and implement By-laws. | Prepare, review, and submit all relevant municipal by-laws to Council for adoption | DEDECT | In-House | Technical Director, NCR Technical Expert | 2027-01-01 | 2027-12-30 | By-law process plan compliance | By-law approval | Financial benefits accruing from improved service delivery efficiencies
6 | PLANNING AND BUIDING CONTROL | Itekeng Extension 3) township has been establishment with objections (whereas Itekeng Extension 2 establishment with pending EIA | Establish a structured engagement plan with the District Municipality to expedite the completion of Blydeville Ext 4 bulk supply connections Schedule monthly technical coordination meetings | NMMDM | In-House | Technical Director, NCR Technical Expert | 2027-01-01 | 2027-12-30 | Township Establishment Approval | Township Establishment Approval | Financial benefits accruing from improved service delivery efficiencies
|  | Blydeville Ext 4 township finalised with no connection to bulk services therefore allocations cannot start. | Scheduling bi-weekly progress review meetings with all appointed service providers. | NMMDM | In-House | Technical Director, NCR Technical Expert | 2027-01-01 | 2027-12-30 | Bulk Service Confirmation | Bulk Service Progress report | Financial benefits accruing from improved service delivery efficiencies
|  |  | Establish a coordinated planning framework to align both processes with spatial planning and environmental regulations, enabling formal proclamation and development approval. | NMMDM | In-House | Technical Director, NCR Technical Expert | 2027-01-01 | 2027-12-30 | Bulk Service Confirmation | Bulk Service Progress report | Financial benefits accruing from improved service delivery efficiencies
|  | Compliance with bylaws is not monitored and enforced. Unlawful land uses and illegal buildings • Resistance to the issue of contraventions notices • Regular building inspections are not conducted | Establish a joint municipal–Human Settlements planning task team to identify, release, and service priority land parcels for housing development | NMMDM | In-House | Technical Director, NCR Technical Expert | 2027-01-01 | 2027-12-30 | Identify, service, release priority land parcels for development | Land Parcel Prioritization Report | Financial benefits accruing from improved service delivery efficiencies
|  |  | Conduct monthly building inspections across all designated zones, ensuring at least 90% of identified non-compliant structures receive contravention notices | NMMDM | In-House | Technical Director, NCR Technical Expert | 2027-01-01 | 2027-12-30 | By-law enforcement plan | By-law enforcement progress report | Financial benefits accruing from improved service delivery efficiencies
7 | FLEET MANAGEMENT | No fleet management policy | Develop and implement a comprehensive Fleet Management Policy. | In-House | In-House | Technical Director, NCR Technical Expert | 2027-01-01 | 2027-12-30 | Reduction in fuel expenditure Vehicle Compliance Elimination of Traffic Fines. Driver Compliance. Consequence Management | Fleet Management Policy | Financial benefits accruing from improved service delivery efficiencies
|  | Inadequate number of refuse vehicles to efficiently service the community Increasing costs make it a challenge to operate efficiently | Develop and implement a fleet replacement and maintenance plan including a scheduled maintenance program for all municipal vehicles | In-House | In-House | Technical Director, NCR Technical Expert | 2027-01-01 | 2027-12-30 | Maintenance allocation of 8% according to NT Cicular 71 norm | Maintenance Plan | Financial benefits accruing from improved service delivery efficiencies
|  | The municipality do not have record or fleet register to establish the number of vehicles to ensure efficient service delivery as information could not be provided. | Develop and maintain a comprehensive fleet register to record for all municipal vehicles and their operational status; Procure and implement a digital fleet management system to ensure accurate data, accountability, and improved service delivery | In-House | In-House | Technical Director, NCR Technical Expert | 2027-01-01 | 2027-12-30 | MIG Allocation for Waste Management | Procurement of refuse vehicle | Financial benefits accruing from improved service delivery efficiencies
8 | HOUSING DELIVERY | The municipality is waiting for notification from the Department of Housing regarding how many units are allocated to Ditsobotla | Establish a structured engagement and reporting framework with the Department of Housing to expedite housing unit allocations and ensure aligned planning | In-House | In-House | Technical Director, NCR Technical Expert | 2027-01-01 | 2027-12-30 | Units allocated to the municipality | Housing allocation to the municipality | Financial benefits accruing from improved service delivery efficiencies
|  | Houses were left at foundation levels by service providers for example in Itsoseng. | Implement a contractor performance management plan that includes: • Conducting monthly performance audits to identify contractors in default • Issuing formal notices to defaulting contractors within 5 business days of audit findings | In-House | In-House | Technical Director, NCR Technical Expert | 2027-01-01 | 2027-12-30 | Project Implementation Plan Compliance. No of notices issued and termination of contracts | Contractor performance management report | Financial benefits accruing from improved service delivery efficiencies
|  | The municipality has not transferred some properties to beneficiaries so they can have their title deeds | Establish a dedicated task team to track and finalize all outstanding transfers. | In-House | In-House | Technical Director, NCR Technical Expert | 2027-01-01 | 2027-12-30 | Full title deed transfer | Progress report on the transfer of title deeds | Financial benefits accruing from improved service delivery efficiencies
|  | Mushrooming of informal settlements around the Municipal area | Strengthen enforcement of spatial planning by-laws and accelerate formalization of suitable informal areas. | In-House | In-House | Technical Director, NCR Technical Expert | 2027-01-01 | 2027-12-30 | Idenfy illegal settlements Identify settlement identify for upgrade Identify settlements for court challenges, eviction and demolition | Informal settlements management progress report | Financial benefits accruing from improved service delivery efficiencies
9 | ROADS AND STORMWATER | Severe deterioration of the roads with potholes and flooding of properties due to blocked or inadequate stormwater systems | Implement a structured Rural Road Maintenance Program by using the Rural Road Asset Management reports to prioritize repairs and maintenance. Conduct quarterly conditional assessments of all rural roads. | In-House | In-House | Technical Director, NCR Technical Expert | 2027-01-01 | 2027-12-30 | sqm of road mainteance | Road Maintenance progress report as per SDBIP | Financial benefits accruing from improved service delivery efficiencies
|  | Gravel roads were not constructed nor maintained | Develop and implement a targeted gravel road maintenance plan that prioritizes construction and grading based on road condition assessments | In-House | In-House | Technical Director, NCR Technical Expert | 2027-01-01 | 2027-12-30 | m2 of road mainteance | Road Maintenance progress report as per SDBIP | Financial benefits accruing from improved service delivery efficiencies
10 | LOCAL ECONOMIC DEVELOPMENT | There is a high level of unemployment skills shortage and inequalities. Huge backlog in the provision of social services, infrastructure, and economic activities. | Partner with TVET colleges, SETAs, and local industries to offer targeted skills training, apprenticeships, and internships targeting unemployed youth and women annually. | In-House | In-House | Technical Director, NCR Technical Expert | 2027-01-01 | 2027-12-30 | LED Strategy Implementation | LED Strategy implementation | Financial benefits accruing from improved service delivery efficiencies
11 | PARKS AND CEMETERIES | Misuse of parks and gardens | Provide rental options and function use for parks and gardens on order to generate revenue | In-House | In-House | Technical Director, NCR Technical Expert | 2027-01-01 | 2027-12-30 | Tariff of charge for facility use | Tariff of charge for facility use | Financial benefits accruing from improved service delivery efficiencies
|  | No proper burial documentation and record keeping at some cemeteries Challenges in the digging of graves Graves are not dug properly and sometimes there are delays | Implement a standardized burial documentation system across all cemeteries in the Ditsobotla municipal area Conduct monthly audits of burial records to ensure at least 95% accuracy and completeness. | In-House | In-House | Technical Director, NCR Technical Expert | 2027-01-01 | 2027-12-30 | Standardized burial documentation system Monthly audits of burial records | Standardized burial documentation system Monthly audits of burial records | Financial benefits accruing from improved service delivery efficiencies

## Phase 3 Sustainability
DITSOBOTLA LOCAL MUNICIPALITY
PHASE 3: SUSTAINABILITY
NO | FOCUS AREA | KEY ASSESSMENT FINDING (BASELINE) | KEY ACTIVITIES | RESOURCES REQUIRED | RESOURCES MOBILISED | RESPONSIBLE | START DATE | END DATE | KEY PERFORMANCE INDICATOR | PoE | BUDGET PARAMETER/ REVENUE TARGET/ SPENDING LIMIT | MUNICIPAL PROGRESS REPORT
[12 empty] | STEPS TAKEN | PROGRESS MADE | FINANCIAL IMPACT | OTHER NOTEWORTHY DEVELOPMENTS
PILLAR ONE: GOOD GOVERNANCE
To be populated after verification of achievements in the rescue and stabilisation phases.
PILLAR TWO: INSTITUTIONAL
To be populated after verification of achievements in the rescue and stabilisation phases.
PILLAR THREE: FINANCIAL MANAGEMENT
To be populated after verification of achievements in the rescue and stabilisation phases.
PILLAR FOUR: SERVICE DELIVERY
To be populated after verification of achievements in the rescue and stabilisation phases.